## Staffing2
Year | Position | Key/Non-Key | Months | FTEs | Rate | Serve as Government point of contact and manage Contractor personnel. | Coordinate kick-off meeting. | Weekly status (meeting agenda, meeting, status report) | Prepare monthly status report. | Coordinate transition-out activities. | Integrate and implement the solution for USPTO products across all product lines. | Enable/promote Virtual DaaS solution usage at the enterprise level. | Integrate and automate the solution into CICD pipeline. | Build a self-service portal for software as a service. | Provision right data at right time to enable testing early, often and faster across all product lines as needed. | Integrate into Agile teams must work with other teams, and vendors, within and across product lines to successfully deliver integrated solutions that achieve USPTO’s goals. | Maintain the Virtual DaaS which must deliver significant savings through storage reclamation and growth spend avoidance. | Provision virtual workloads in minutes for Test/Dev, Labs/Training & integrate with Orchestration / configuration mgmt. tools like Chef, Puppet & Ansible. | Enable the Virtual DaaS system use of multiple cloud providers as required. | Manage data on-premise and in multiple cloud providers via a single solution as required. | Make right data available and make data available for all aspects of development, testing and other cross-functional teams. | Provide a Corrective Action Plan. | Create and analyze user stories and/or requirements as data replication service defined by an Agile team. | Implement data replications services. | Analyze critically current implementation of replication solution and list the challenges and steps for improvements. | Implement the solution such as configuration & troubleshooting for test data management | Implement the solution for a different types of databases such as RDBMS, NoSQL, cloud DBs, and others as needed across USPTO product lines. | Develop Technical documentation such as System Design Document (SDD), Operating Support Procedures (SOP) and any other type of documentation as required by Agile Delivery Office, Agile team, and OCIO standards. | Manage issues in compliance with NWOW organizational structure. | Implement, maintain and enhance the capability of automated virtual data provisioning utilizing API (e.g. Actifio API) programmatically, with or without a self-service web portal or tools used in the CI/CD pipeline build process. | Contribute in the scoping and planning of Virtual DaaS self-service portal for each product team. | Support Virtual DaaS COTS product (Actifio) operation and maintenance activities | Define the Data as a Service Strategy, High-Level Roadmap for solution components & ROI/CBA. | Identifying and interviewing core stakeholders involved in end-to-end processes. | Reviewing the current process interactions, configuration of environments & data, support team alignment, KPI & artifacts to interdependencies across processes. | Identifying the opportunities for improvements along with recommendations for Planning and Solution Design phase. | The contractor shall conduct all aspects of testing. | The contractor shall conduct research investigation to implement Virtual DaaS cloud migration and implementation in compliance with USPTO cloud implementation procedures and standards. The contractor shall apply industry best practices to deliver value during daily work in implementation, operation and customer services. |  | Serve as Government point of contact and manage Contractor personnel. | Coordinate kick-off meeting. | Weekly status (meeting agenda, meeting, status report) | Prepare monthly status report. | Coordinate transition-out activities. | Integrate and implement the solution for USPTO products across all product lines. | Enable/promote Virtual DaaS solution usage at the enterprise level. | Integrate and automate the solution into CICD pipeline. | Build a self-service portal for software as a service. | Provision right data at right time to enable testing early, often and faster across all product lines as needed. | Integrate into Agile teams must work with other teams, and vendors, within and across product lines to successfully deliver integrated solutions that achieve USPTO’s goals. | Maintain the Virtual DaaS which must deliver significant savings through storage reclamation and growth spend avoidance. | Provision virtual workloads in minutes for Test/Dev, Labs/Training & integrate with Orchestration / configuration mgmt. tools like Chef, Puppet & Ansible. | Enable the Virtual DaaS system use of multiple cloud providers as required. | Manage data on-premise and in multiple cloud providers via a single solution as required. | Make right data available and make data available for all aspects of development, testing and other cross-functional teams. | Provide a Corrective Action Plan. | Create and analyze user stories and/or requirements as data replication service defined by an Agile team. | Implement data replications services. | Analyze critically current implementation of replication solution and list the challenges and steps for improvements. | Implement the solution such as configuration & troubleshooting for test data management | Implement the solution for a different types of databases such as RDBMS, NoSQL, cloud DBs, and others as needed across USPTO product lines. | Develop Technical documentation such as System Design Document (SDD), Operating Support Procedures (SOP) and any other type of documentation as required by Agile Delivery Office, Agile team, and OCIO standards. | Manage issues in compliance with NWOW organizational structure. | Implement, maintain and enhance the capability of automated virtual data provisioning utilizing API (e.g. Actifio API) programmatically, with or without a self-service web portal or tools used in the CI/CD pipeline build process. | Contribute in the scoping and planning of Virtual DaaS self-service portal for each product team. | Support Virtual DaaS COTS product (Actifio) operation and maintenance activities | Define the Data as a Service Strategy, High-Level Roadmap for solution components & ROI/CBA. | Identifying and interviewing core stakeholders involved in end-to-end processes. | Reviewing the current process interactions, configuration of environments & data, support team alignment, KPI & artifacts to interdependencies across processes. | Identifying the opportunities for improvements along with recommendations for Planning and Solution Design phase. | The contractor shall conduct all aspects of testing. | The contractor shall conduct research investigation to implement Virtual DaaS cloud migration and implementation in compliance with USPTO cloud implementation procedures and standards. The contractor shall apply industry best practices to deliver value during daily work in implementation, operation and customer services. | Total Hours | Annual Price | Annual Total
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 |  |  |  |  | Hours Summary by Task Area
[6 empty] | C.4.1 | C.4.1 | C.4.1 | C.4.1 | C.4.1 | C.4.2 | C.4.2 | C.4.2 | C.4.5 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.4 | C.4.3 | C.4.3 | C.4.3 | C.4.3 | C.4.6 | C.4.4 | C.4.5 | C.4.9 | C.4.5 | C.4.7 | C.4.7 | C.4.7 | C.4.7 | C.4.8 | C.4.9 |  | C.4.1 | C.4.1 | C.4.1 | C.4.1 | C.4.1 | C.4.2 | C.4.2 | C.4.2 | C.4.5 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.2 | C.4.4 | C.4.3 | C.4.3 | C.4.3 | C.4.3 | C.4.6 | C.4.4 | C.4.5 | C.4.9 | C.4.5 | C.4.7 | C.4.7 | C.4.7 | C.4.7 | C.4.8 | C.4.9 |  |  |  |  | C.4.1 | C.4.2 | C.4.3 | C.4.4 | C.4.5 | C.4.6 | C.4.7 | C.4.8 | C.4.9 | Total
1 | Senior DBA | Key | 12 | 1 | 110.74 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 212510.06 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
1 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 129.48 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 248472.12 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
1 | SME Software Developer, Applications and Systems Software | Key | 12 | 1 | 158.44 | 0% | 0% | 0% | 0% | 0% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 99.96% | 0 | 0 | 0 | 0 | 0 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 68.5083 | 1918.2324 | 303924.7415 |  |  | 0 | 753.5913 | 274.0332 | 137.0166 | 205.5249 | 68.5083 | 274.0332 | 68.5083 | 137.0166 | 1918.2324
1 | DBA | Non-Key | 9 | 1 | 91.57 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 14.3925 | 14.3925 | 14.3925 | 71.9625 | 14.3925 | 719.625 | 14.3925 | 14.3925 | 28.785 | 14.3925 | 14.3925 | 14.3925 | 14.3925 | 43.1775 | 14.3925 | 43.1775 | 43.1775 | 71.9625 | 14.3925 | 43.1775 | 71.9625 | 28.785 | 14.3925 | 14.3925 | 14.3925 | 14.3925 | 28.785 | 14.3925 | 1439.25 | 131792.1225 |  |  | 0 | 877.9425 | 143.925 | 28.785 | 143.925 | 71.9625 | 57.57 | 28.785 | 86.355 | 1439.25
1 | Journeyman Software Developer, Applications and System Software | Non-Key | 9 | 1 | 107.33 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 71.9625 | 0 | 0 | 719.625 | 0 | 374.205 | 0 | 0 | 0 | 0 | 0 | 0 | 28.785 | 28.785 | 14.3925 | 14.3925 | 14.3925 | 28.785 | 0 | 71.9625 | 14.3925 | 14.3925 | 0 | 0 | 0 | 0 | 43.1775 | 0 | 1439.25 | 154474.7025 |  |  | 0 | 446.1675 | 71.9625 | 28.785 | 805.98 | 28.785 | 0 | 43.1775 | 14.3925 | 1439.25
1 | Testing Engineer | Non-Key | 9 | 1 | 76.37 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.25 | 0 | 1439.25 | 109915.5225 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.25 | 0 | 1439.25
1 | Senior Testing Engineer | Non-Key | 9 | 1 | 111.3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.25 | 0 | 1439.25 | 160188.525 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.25 | 0 | 1439.25
1 | Project Manager | Non-Key | 12 | 0.5 | 100.52 | 22.4% | 8.6% | 33.7% | 10.3% | 9.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.3% | 0% | 0% | 11.2% | 0% | 0% | 100% | 214.928 | 82.517 | 323.3515 | 98.8285 | 91.1525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.2585 | 0 | 0 | 107.464 | 0 | 0 | 959.5 | 96448.94 | 1417726.734 |  | 810.7775 | 0 | 0 | 0 | 0 | 0 | 148.7225 | 0 | 0 | 959.5
2 | Senior DBA | Key | 12 | 1 | 112.9548 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 216760.2612 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
2 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 132.0696 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 253441.5624 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
2 | SME Software Developer, Applications and Systems Software | Key | 12 | 0 | 161.6088 | 0% | 0% | 0% | 0% | 0% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 99.96% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | DBA | Non-Key | 12 | 1 | 93.4014 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 179237.2866 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
2 | Journeyman Software Developer, Applications and System Software | Non-Key | 12 | 1 | 109.4766 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 210085.5954 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
2 | Testing Engineer | Non-Key | 12 | 1 | 77.8974 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919 | 149485.1106 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919
2 | Senior Testing Engineer | Non-Key | 12 | 1 | 113.526 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919 | 217856.394 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919
2 | Project Manager | Non-Key | 12 | 0.5 | 102.5304 | 26.3% | 0% | 39.4% | 12.1% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.1% | 0% | 0% | 13.1% | 0% | 0% | 100% | 252.3485 | 0 | 378.043 | 116.0995 | 57.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7445 | 0 | 0 | 125.6945 | 0 | 0 | 959.5 | 98377.9188 | 1325244.129 |  | 804.061 | 0 | 0 | 0 | 0 | 0 | 155.439 | 0 | 0 | 959.5
3 | Senior DBA | Key | 12 | 1 | 115.2139 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 221095.4664 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
3 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 134.711 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 258510.3936 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
3 | SME Software Developer, Applications and Systems Software | Key | 12 | 0 | 164.841 | 0% | 0% | 0% | 0% | 0% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 99.96% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | DBA | Non-Key | 12 | 1 | 95.2694 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 182822.0323 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
3 | Journeyman Software Developer, Applications and System Software | Non-Key | 12 | 1 | 111.6661 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 214287.3073 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
3 | Testing Engineer | Non-Key | 12 | 1 | 79.4553 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919 | 152474.8128 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919
3 | Senior Testing Engineer | Non-Key | 12 | 1 | 115.7965 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919 | 222213.5219 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919
3 | Project Manager | Non-Key | 12 | 0.5 | 104.581 | 26.3% | 0% | 39.4% | 12.1% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.1% | 0% | 0% | 13.1% | 0% | 0% | 100% | 252.3485 | 0 | 378.043 | 116.0995 | 57.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7445 | 0 | 0 | 125.6945 | 0 | 0 | 959.5 | 100345.4772 | 1351749.0116 |  | 804.061 | 0 | 0 | 0 | 0 | 0 | 155.439 | 0 | 0 | 959.5
4 | Senior DBA | Key | 12 | 1 | 117.5182 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 225517.3758 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
4 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 137.4052 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 263680.6015 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
4 | SME Software Developer, Applications and Systems Software | Key | 12 | 0 | 168.1378 | 0% | 0% | 0% | 0% | 0% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 3.57% | 99.96% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DBA | Non-Key | 12 | 1 | 97.1748 | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 1% | 5% | 1% | 50% | 1% | 1% | 2% | 1% | 1% | 1% | 1% | 3% | 1% | 3% | 3% | 5% | 1% | 3% | 5% | 2% | 1% | 1% | 1% | 1% | 2% | 1% | 100% | 0 | 0 | 0 | 0 | 0 | 19.19 | 19.19 | 19.19 | 95.95 | 19.19 | 959.5 | 19.19 | 19.19 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 57.57 | 19.19 | 57.57 | 57.57 | 95.95 | 19.19 | 57.57 | 95.95 | 38.38 | 19.19 | 19.19 | 19.19 | 19.19 | 38.38 | 19.19 | 1919 | 186478.473 |  |  | 0 | 1170.59 | 191.9 | 38.38 | 191.9 | 95.95 | 76.76 | 38.38 | 115.14 | 1919
4 | Journeyman Software Developer, Applications and System Software | Non-Key | 12 | 1 | 113.8995 | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 50% | 0% | 26% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% | 1% | 1% | 1% | 2% | 0% | 5% | 1% | 1% | 0% | 0% | 0% | 0% | 3% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 95.95 | 0 | 0 | 959.5 | 0 | 498.94 | 0 | 0 | 0 | 0 | 0 | 0 | 38.38 | 38.38 | 19.19 | 19.19 | 19.19 | 38.38 | 0 | 95.95 | 19.19 | 19.19 | 0 | 0 | 0 | 0 | 57.57 | 0 | 1919 | 218573.0535 |  |  | 0 | 594.89 | 95.95 | 38.38 | 1074.64 | 38.38 | 0 | 57.57 | 19.19 | 1919
4 | Testing Engineer | Non-Key | 12 | 1 | 81.0445 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919 | 155524.3091 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919
4 | Senior Testing Engineer | Non-Key | 12 | 1 | 118.1125 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919 | 226657.7923 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 1919
4 | Project Manager | Non-Key | 12 | 0.5 | 106.6726 | 24.4% | 0% | 36.7% | 11.2% | 12.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.9% | 0% | 0% | 12.2% | 0% | 0% | 100% | 234.118 | 0 | 352.1365 | 107.464 | 120.897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.8255 | 0 | 0 | 117.059 | 0 | 0 | 959.5 | 102352.3867 | 1378783.9918 |  | 814.6155 | 0 | 0 | 0 | 0 | 0 | 144.8845 | 0 | 0 | 959.5
[40 empty] | 953.743 | 82.517 | 1431.574 | 438.4915 | 327.1895 | 960.8433 | 217.2308 | 217.2308 | 8248.2458 | 217.2308 | 11371.4183 | 217.2308 | 217.2308 | 365.9533 | 217.2308 | 217.2308 | 217.2308 | 514.6758 | 812.1208 | 365.9533 | 663.3983 | 663.3983 | 1109.5658 | 217.2308 | 1258.2883 | 960.8433 | 514.6758 | 345.8038 | 217.2308 | 217.2308 | 693.1428 | 15204.6208 | 217.2308 | 49893.2324 | 5473503.8663 | 5473503.8663 |  | 3233.515 | 14436.0613 | 2504.8707 | 731.9066 | 10021.2099 | 1109.5658 | 1473.4082 | 15204.6208 | 1178.0741 | 49893.2324
[40 empty] | 1.912% | 0.1654% | 2.869% | 0.8789% | 0.6558% | 1.926% | 0.4354% | 0.4354% | 16.53% | 0.4354% | 22.79% | 0.4354% | 0.4354% | 0.7335% | 0.4354% | 0.4354% | 0.4354% | 1.032% | 1.628% | 0.7335% | 1.33% | 1.33% | 2.224% | 0.4354% | 2.522% | 1.926% | 1.032% | 0.6931% | 0.4354% | 0.4354% | 1.389% | 30.47% | 0.4354% |  |  |  |  | 6.481% | 28.93% | 5.02% | 1.467% | 20.09% | 2.224% | 2.953% | 30.47% | 2.361% | 100%
[72 empty] | 100% |  |  |  |  | PM | Integ | Imp | Reqs | Dev | Doc | Analysis | Test | Planning
[6 empty] | 33: Year 1 | Total Hours | 214.928 | 82.517 | 323.3515 | 98.8285 | 91.1525 | 270.0033 | 102.0908 | 102.0908 | 1915.5458 | 102.0908 | 2620.7783 | 102.0908 | 102.0908 | 135.6733 | 102.0908 | 102.0908 | 102.0908 | 169.2558 | 236.4208 | 135.6733 | 202.8383 | 202.8383 | 303.5858 | 102.0908 | 337.1683 | 270.0033 | 169.2558 | 143.3493 | 102.0908 | 102.0908 | 209.5548 | 3114.9208 | 102.0908 | 12472.7324 |  | Year 1 | Total Hours | 810.7775 | 3843.1813 | 777.7707 | 271.3466 | 2421.9699 | 303.5858 | 557.0857 | 3114.9208 | 372.0941 | 12472.7324
[39 empty] | Pct | 1.723% | 0.6616% | 2.592% | 0.7924% | 0.7308% | 2.165% | 0.8185% | 0.8185% | 15.36% | 0.8185% | 21.01% | 0.8185% | 0.8185% | 1.088% | 0.8185% | 0.8185% | 0.8185% | 1.357% | 1.896% | 1.088% | 1.626% | 1.626% | 2.434% | 0.8185% | 2.703% | 2.165% | 1.357% | 1.149% | 0.8185% | 0.8185% | 1.68% | 24.97% | 0.8185% | 100% |  |  | Pct | 6.5% | 30.81% | 6.236% | 2.176% | 19.42% | 2.434% | 4.466% | 24.97% | 2.983% | 100%
[6 empty] | 33: Year 2 | Total Hours | 252.3485 | 0 | 378.043 | 116.0995 | 57.57 | 230.28 | 38.38 | 38.38 | 2110.9 | 38.38 | 2916.88 | 38.38 | 38.38 | 76.76 | 38.38 | 38.38 | 38.38 | 115.14 | 191.9 | 76.76 | 153.52 | 153.52 | 268.66 | 38.38 | 307.04 | 230.28 | 115.14 | 68.1245 | 38.38 | 38.38 | 164.0745 | 4029.9 | 38.38 | 12473.5 |  | Year 2 | Total Hours | 804.061 | 3530.96 | 575.7 | 153.52 | 2533.08 | 268.66 | 308.959 | 4029.9 | 268.66 | 12473.5
[39 empty] | Pct | 2.023% | 0% | 3.031% | 0.9308% | 0.4615% | 1.846% | 0.3077% | 0.3077% | 16.92% | 0.3077% | 23.38% | 0.3077% | 0.3077% | 0.6154% | 0.3077% | 0.3077% | 0.3077% | 0.9231% | 1.538% | 0.6154% | 1.231% | 1.231% | 2.154% | 0.3077% | 2.462% | 1.846% | 0.9231% | 0.5462% | 0.3077% | 0.3077% | 1.315% | 32.31% | 0.3077% | 100% |  |  | Pct | 6.446% | 28.31% | 4.615% | 1.231% | 20.31% | 2.154% | 2.477% | 32.31% | 2.154% | 100%
[6 empty] | 33: Year 3 | Total Hours | 252.3485 | 0 | 378.043 | 116.0995 | 57.57 | 230.28 | 38.38 | 38.38 | 2110.9 | 38.38 | 2916.88 | 38.38 | 38.38 | 76.76 | 38.38 | 38.38 | 38.38 | 115.14 | 191.9 | 76.76 | 153.52 | 153.52 | 268.66 | 38.38 | 307.04 | 230.28 | 115.14 | 68.1245 | 38.38 | 38.38 | 164.0745 | 4029.9 | 38.38 | 12473.5 |  | Year 3 | Total Hours | 804.061 | 3530.96 | 575.7 | 153.52 | 2533.08 | 268.66 | 308.959 | 4029.9 | 268.66 | 12473.5
[39 empty] | Pct | 2.023% | 0% | 3.031% | 0.9308% | 0.4615% | 1.846% | 0.3077% | 0.3077% | 16.92% | 0.3077% | 23.38% | 0.3077% | 0.3077% | 0.6154% | 0.3077% | 0.3077% | 0.3077% | 0.9231% | 1.538% | 0.6154% | 1.231% | 1.231% | 2.154% | 0.3077% | 2.462% | 1.846% | 0.9231% | 0.5462% | 0.3077% | 0.3077% | 1.315% | 32.31% | 0.3077% | 100% |  |  | Pct | 6.446% | 28.31% | 4.615% | 1.231% | 20.31% | 2.154% | 2.477% | 32.31% | 2.154% | 100%
[6 empty] | 33: Year 4 | Total Hours | 234.118 | 0 | 352.1365 | 107.464 | 120.897 | 230.28 | 38.38 | 38.38 | 2110.9 | 38.38 | 2916.88 | 38.38 | 38.38 | 76.76 | 38.38 | 38.38 | 38.38 | 115.14 | 191.9 | 76.76 | 153.52 | 153.52 | 268.66 | 38.38 | 307.04 | 230.28 | 115.14 | 66.2055 | 38.38 | 38.38 | 155.439 | 4029.9 | 38.38 | 12473.5 |  | Year 4 | Total Hours | 814.6155 | 3530.96 | 575.7 | 153.52 | 2533.08 | 268.66 | 298.4045 | 4029.9 | 268.66 | 12473.5
[39 empty] | Pct | 1.877% | 0% | 2.823% | 0.8615% | 0.9692% | 1.846% | 0.3077% | 0.3077% | 16.92% | 0.3077% | 23.38% | 0.3077% | 0.3077% | 0.6154% | 0.3077% | 0.3077% | 0.3077% | 0.9231% | 1.538% | 0.6154% | 1.231% | 1.231% | 2.154% | 0.3077% | 2.462% | 1.846% | 0.9231% | 0.5308% | 0.3077% | 0.3077% | 1.246% | 32.31% | 0.3077% | 100% |  |  | Pct | 6.531% | 28.31% | 4.615% | 1.231% | 20.31% | 2.154% | 2.392% | 32.31% | 2.154% | 100%

## Staffing
Year | Position | Key/Non-Key | Months | FTEs | Rate | Provide Product Management Support | Integration of Virtual DaaS in Product Development Across All Product Lines | Implementation and Integration of Virtual DaaS Replication Solution | Communication and Requirement | Implementation, Operation and Customer Services | Documentation and Compliance | Phased Adoption and Approach for DaaS & Disaster Recovery (DR) | Automated Testing | Design, Implementation, Operation and Customer Services |  | Provide Product Management Support | Integration of Virtual DaaS in Product Development Across All Product Lines | Implementation and Integration of Virtual DaaS Replication Solution | Communication and Requirement | Implementation, Operation and Customer Services | Documentation and Compliance | Phased Adoption and Approach for DaaS & Disaster Recovery (DR) | Automated Testing | Design, Implementation, Operation and Customer Services | Total Hours | Annual Price | Annual Total
[6 empty] | C.4. 1 | C.4.2 | C.4.3 | C.4.4 | C.4.5 | C.4.6 | C.4.7 | C.4.8 | C.4.9 |  | C.4. 1 | C.4.2 | C.4.3 | C.4.4 | C.4.5 | C.4.6 | C.4.7 | C.4.8 | C.4.9
1 | Senior DBA | Key | 12 | 1 | 110.74 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 212510.06
1 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 129.48 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 248472.12
1 | SME Software Developer, Applications and Systems Software | Key | 12 | 1 | 158.44 | 0% | 15% | 15% | 10% | 10% | 10% | 15% | 5% | 15% | 95% | 0 | 287.85 | 287.85 | 191.9 | 191.9 | 191.9 | 287.85 | 95.95 | 287.85 | 1823.05 | 288844.042
1 | DBA | Non-Key | 9 | 1 | 91.57 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 179.9062 | 179.9062 | 179.9062 | 179.9062 | 179.9062 | 179.9062 | 179.9062 | 179.9062 | 1439.25 | 131792.1225
1 | Journeyman Software Developer, Applications and System Software | Non-Key | 9 | 1 | 107.33 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 359.8125 | 0 | 359.8125 | 179.9062 | 0 | 179.9062 | 359.8125 | 1439.25 | 154474.7025
1 | Testing Engineer | Non-Key | 9 | 1 | 76.37 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 143.925 | 215.8875 | 0 | 863.55 | 215.8875 | 1439.25 | 109915.5225
1 | Senior Testing Engineer | Non-Key | 9 | 1 | 111.3 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 143.925 | 215.8875 | 0 | 863.55 | 215.8875 | 1439.25 | 160188.525
1 | Project Manager | Non-Key | 12 | 0.5 | 100.52 | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100% | 479.75 | 0 | 0 | 0 | 0 | 0 | 479.75 | 0 | 0 | 959.5 | 96448.94 | 1402646.0345
2 | Senior DBA | Key | 12 | 1 | 112.9548 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 216760.2612
2 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 132.0696 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 253441.5624
2 | SME Software Developer, Applications and Systems Software | Key | 12 | 0 | 161.6088 | 0% | 15% | 15% | 10% | 10% | 10% | 15% | 5% | 15% | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | DBA | Non-Key | 12 | 1 | 93.4014 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 179237.2866
2 | Journeyman Software Developer, Applications and System Software | Non-Key | 12 | 1 | 109.4766 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 210085.5954
2 | Testing Engineer | Non-Key | 12 | 1 | 77.8974 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 191.9 | 287.85 | 0 | 1151.4 | 287.85 | 1919 | 149485.1106
2 | Senior Testing Engineer | Non-Key | 12 | 1 | 113.526 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 191.9 | 287.85 | 0 | 1151.4 | 287.85 | 1919 | 217856.394
2 | Project Manager (.25 FTE) | Non-Key | 12 | 0.5 | 102.5304 | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100% | 479.75 | 0 | 0 | 0 | 0 | 0 | 479.75 | 0 | 0 | 959.5 | 98377.9188 | 1325244.129
3 | Senior DBA | Key | 12 | 1 | 115.2139 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 221095.4664
3 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 134.711 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 258510.3936
3 | SME Software Developer, Applications and Systems Software | Key | 12 | 0 | 164.841 | 0% | 15% | 15% | 10% | 10% | 10% | 15% | 5% | 15% | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | DBA | Non-Key | 12 | 1 | 95.2694 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 182822.0323
3 | Journeyman Software Developer, Applications and System Software | Non-Key | 12 | 1 | 111.6661 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 214287.3073
3 | Testing Engineer | Non-Key | 12 | 1 | 79.4553 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 191.9 | 287.85 | 0 | 1151.4 | 287.85 | 1919 | 152474.8128
3 | Senior Testing Engineer | Non-Key | 12 | 1 | 115.7965 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 191.9 | 287.85 | 0 | 1151.4 | 287.85 | 1919 | 222213.5219
3 | Project Manager (.25 FTE) | Non-Key | 12 | 0.5 | 104.581 | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100% | 479.75 | 0 | 0 | 0 | 0 | 0 | 479.75 | 0 | 0 | 959.5 | 100345.4772 | 1351749.0116
4 | Senior DBA | Key | 12 | 1 | 117.5182 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 225517.3758
4 | Senior Software Developer, Applications and Systems Software | Key | 12 | 1 | 137.4052 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 263680.6015
4 | SME Software Developer, Applications and Systems Software | Key | 12 | 0 | 168.1378 | 0% | 15% | 15% | 10% | 10% | 10% | 15% | 5% | 15% | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DBA | Non-Key | 12 | 1 | 97.1748 | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 0 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 239.875 | 1919 | 186478.473
4 | Journeyman Software Developer, Applications and System Software | Non-Key | 12 | 1 | 113.8995 | 0% | 0% | 25% | 0% | 25% | 12.5% | 0% | 12.5% | 25% | 100% | 0 | 0 | 479.75 | 0 | 479.75 | 239.875 | 0 | 239.875 | 479.75 | 1919 | 218573.0535
4 | Testing Engineer | Non-Key | 12 | 1 | 81.0445 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 191.9 | 287.85 | 0 | 1151.4 | 287.85 | 1919 | 155524.3091
4 | Senior Testing Engineer | Non-Key | 12 | 1 | 118.1125 | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 60% | 15% | 100% | 0 | 0 | 0 | 0 | 191.9 | 287.85 | 0 | 1151.4 | 287.85 | 1919 | 226657.7923
4 | Project Manager (.25 FTE) | Non-Key | 12 | 0.5 | 106.6726 | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 100% | 479.75 | 0 | 0 | 0 | 0 | 0 | 479.75 | 0 | 0 | 959.5 | 102352.3867 | 1378783.9918
[16 empty] | 1919 | 2146.8812 | 5864.9438 | 2050.9313 | 7208.2437 | 6068.8375 | 4065.8812 | 12449.5125 | 8023.8188 | 49798.05 | 5458423.1669 | 5458423.1669
[16 empty] | 3.854% | 4.311% | 11.78% | 4.118% | 14.47% | 12.19% | 8.165% | 25% | 16.11%

## Task
Task Area No | Task Area Description | LU | Year 1 | Year 2 | Year 3 | Year 4
C.4. 1 | Provide Product Management Support | C.4. 1 | 25% | 25% | 25% | 25%
C.4.1.1 | Coordinate a Kick-Off Meeting | C.4.1.1 | 100%
C.4.1.2 | Prepare a Weekly Status Report (WSR) | C.4.1.2 | 25% | 25% | 25% | 25%
C.4.1.3 | Monthly Status Report (MSR) | C.4.1.3 | 25% | 25% | 25% | 25%
C.4.1.5 | Transition-Out | C.4.1.5 | 30% | 15% | 15% | 40%
C.4.2 | Integration of Virtual DaaS in Product Development Across All Product Lines | C.4.2 | 25% | 25% | 25% | 25%
C.4.3 | Implementation and Integration of Virtual DaaS Replication Solution | C.4.3 | 25% | 25% | 25% | 25%
C.4.4 | Communication and Requirement | C.4.4 | 25% | 25% | 25% | 25%
C.4.5 | Implementation, Operation and Customer Services | C.4.5 | 25% | 25% | 25% | 25%
C.4.6 | Documentation and Compliance | C.4.6 | 25% | 25% | 25% | 25%
C.4.7 | Phased Adoption and Approach for DaaS & Disaster Recovery (DR) | C.4.7 | 25% | 25% | 25% | 25%
C.4.8 | Automated Testing | C.4.8 | 25% | 25% | 25% | 25%
C.4.9 | Design, Implementation, Operation and Customer Services | C.4.9 | 25% | 25% | 25% | 25%

## TaskAnalysis
Overlap Anaysis for Tasks |  |  | Task Areas
|  |  | Provide Product Management Support (Project Management) | Integration of Virtual DaaS in Product Development Across All Product Lines (Integration) | Implementation and Integration of Virtual DaaS Replication Solution (Replication Implementation) | Communication and Requirement (Requirements) | Implementation, Operation and Customer Services (Build / Operations) | Documentation and Compliance (Documentation / Security) | Phased Adoption and Approach for DaaS & Disaster Recovery (DR) (Analysis) | Automated Testing (Testing) | Design, Implementation, Operation and Customer Services (Planning / Research) | Senior DBA | Senior Software Developer, Applications and Systems Software | SME Software Developer, Applications and Systems Software | DBA | Journeyman Software Developer, Applications and System Software | Testing Engineer | Senior Testing Engineer | Project Manager | BA
Task No | Task Description | Task Area | C.4. 1 | C.4.2 | C.4.3 | C.4.4 | C.4.5 | C.4.6 | C.4.7 | C.4.8 | C.4.9
1 | Serve as Government point of contact and manage Contractor personnel. | C.4. 1 | [16 empty] | 22.4% | bar: C.4. 1
2 | Coordinate kick-off meeting. | C.4. 1 | [16 empty] | 8.6% | bar: C.4. 1
3 | Weekly status (meeting agenda, meeting, status report) | C.4. 1 | [16 empty] | 33.7% | bar: C.4. 1
4 | Prepare monthly status report. | C.4. 1 | [16 empty] | 10.3% | bar: C.4. 1
5 | Coordinate transition-out activities. | C.4. 1 | [16 empty] | 9.5% | bar: C.4. 1
6 | Integrate and implement the solution for USPTO products across all product lines. | C.4.2 | [9 empty] | 1% | 5% | 3.57% | 1% | 5% | bar: C.4.2; C.4.7
7 | Enable/promote Virtual DaaS solution usage at the enterprise level. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% | bar: C.4.2
8 | Integrate and automate the solution into CICD pipeline. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% | bar: C.4.2
9 | Build a self-service portal for software as a service. | C.4.5 | [9 empty] | 5% | 50% | 3.57% | 5% | 50% | bar: C.4.2; C.4.5; C.4.9
10 | Provision right data at right time to enable testing early, often and faster across all product lines as needed. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% | bar: C.4.2
11 | Integrate into Agile teams must work with other teams, and vendors, within and across product lines to successfully deliver integrated solutions that achieve USPTO’s goals. | C.4.2 | [9 empty] | 50% | 26% | 3.57% | 50% | 26% |  |  |  | x | bar: C.4.2 to C.4.5; C.4.9
12 | Maintain the Virtual DaaS which must deliver significant savings through storage reclamation and growth spend avoidance. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  |  | x | bar: C.4.2
13 | Provision virtual workloads in minutes for Test/Dev, Labs/Training & integrate with Orchestration / configuration mgmt. tools like Chef, Puppet & Ansible. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% | bar: C.4.2
14 | Enable the Virtual DaaS system use of multiple cloud providers as required. | C.4.2 | [9 empty] | 2% |  | 3.57% | 2% | bar: C.4.2
15 | Manage data on-premise and in multiple cloud providers via a single solution as required. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% | bar: C.4.2
16 | Make right data available and make data available for all aspects of development, testing and other cross-functional teams. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% | bar: C.4.2
17 | Provide a Corrective Action Plan. | C.4.2 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  |  | x | bar: C.4.2
18 | Create and analyze user stories and/or requirements as data replication service defined by an Agile team. | C.4.4 | [9 empty] | 1% | 2% | 3.57% | 1% | 2% |  |  |  | x | bar: C.4.3 to C.4.4
19 | Implement data replications services. | C.4.3 | [9 empty] | 3% | 2% | 3.57% | 3% | 2% | bar: C.4.3
20 | Analyze critically current implementation of replication solution and list the challenges and steps for improvements. | C.4.3 | [9 empty] | 1% | 1% | 3.57% | 1% | 1% |  |  |  | x | bar: C.4.3
21 | Implement the solution such as configuration & troubleshooting for test data management | C.4.3 | [9 empty] | 3% | 1% | 3.57% | 3% | 1% | bar: C.4.3
22 | Implement the solution for a different types of databases such as RDBMS, NoSQL, cloud DBs, and others as needed across USPTO product lines. | C.4.3 | [9 empty] | 3% | 1% | 3.57% | 3% | 1% | bar: C.4.3
23 | Develop Technical documentation such as System Design Document (SDD), Operating Support Procedures (SOP) and any other type of documentation as required by Agile Delivery Office, Agile team, and OCIO standards. | C.4.6 | [9 empty] | 5% | 2% | 3.57% | 5% | 2% |  |  |  | x | bar: C.4.3; C.4.6
24 | Manage issues in compliance with NWOW organizational structure. | C.4.4 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  |  | x | bar: C.4.4
25 | Implement, maintain and enhance the capability of automated virtual data provisioning utilizing API (e.g. Actifio API) programmatically, with or without a self-service web portal or tools used in the CI/CD pipeline build process. | C.4.5 | [9 empty] | 3% | 5% | 3.57% | 3% | 5% | 0% | 0% | bar: C.4.5; C.4.9
26 | Contribute in the scoping and planning of Virtual DaaS self-service portal for each product team. | C.4.9 | [9 empty] | 5% | 1% | 3.57% | 5% | 1% | 0% | 0% |  | x | bar: C.4.5; C.4.9
27 | Support Virtual DaaS COTS product (Actifio) operation and maintenance activities | C.4.5 | [9 empty] | 2% | 1% | 3.57% | 2% | 1% | 0% | 0% | bar: C.4.5; C.4.9
28 | Define the Data as a Service Strategy, High-Level Roadmap for solution components & ROI/CBA. | C.4.7 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  | 4.3% | x | bar: C.4.7
29 | Identifying and interviewing core stakeholders involved in end-to-end processes. | C.4.7 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  | 0% | x | bar: C.4.7
30 | Reviewing the current process interactions, configuration of environments & data, support team alignment, KPI & artifacts to interdependencies across processes. | C.4.7 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  | 0% | x | bar: C.4.7
31 | Identifying the opportunities for improvements along with recommendations for Planning and Solution Design phase. | C.4.7 | [9 empty] | 1% |  | 3.57% | 1% |  |  |  | 11.2% | x | bar: C.4.7
32 | The contractor shall conduct all aspects of testing. | C.4.8 | [9 empty] | 2% | 3% | 3.57% | 2% | 3% | 100% | 100% | bar: C.4.8
33 | The contractor shall conduct research investigation to implement Virtual DaaS cloud migration and implementation in compliance with USPTO cloud implementation procedures and standards. The contractor shall apply industry best practices to deliver value during daily work in implementation, operation and customer services. | C.4.9 | [9 empty] | 1% | 0% | 3.57% | 1% | 0% | 0% | 0% |  | x | bar: C.4.9
|  |  | C.4. 1: 0 | 100% | 100% | 99.96% | 100% | 100% | 100% | 100% | 100%
[12 empty] | 28 | 13 | 28 | 28 | 13 | 1 | 1 | 7 | ←Count
[12 empty] | 3.571% | 7.692% | 3.571% | 3.571% | 7.692% | 100% | 100% | 14.29% | ←Avg

## Deliverable
Deliverable No | Description | LU
1 | Kick-off meeting(s) | 1
2 | Weekly Status Report | 2
3 | Monthly Status Report | 3
4 | Hourly reports, Actual A, Actual B, Invoices, Raw file etc. | 4
5 | Meeting Agendas, Minutes, Action Items, monthly vendor meetings | 5
6 | Transition Plan | 6
7 | Automated Test Code and associated data | 7
8 | Test Plans, Data, Script and Results | 8
9 | Root Cause Analysis and Remediation Report | 9
10 | Remediation Plan | 10
11 | Virtual Data Provision Programmatically using Virtual Data System API | 11
12 | End User Self-Service Web Portal | 12
13 | ATO required documentations | 13
14 | Agile ceremonies, NWOW, DevSecOps | 14
15 | Technical Issue Report & Logging | 15
16 | Technical Issue Resolution | 16
17 | Support and Maintain Virtual DaaS System, Self-Service Web Portal and Tools as Documented in Rally | 17
18 | Customer Support on Virutal DaaS System | 18
19 | Actifio GO Migration | 19
20 | Road Map and Release Plans (Solution implementation Roadmap) | 20
21 | Functional API Scripts (Solution implementation Roadmap) | 21
22 | Self-Service Web Portal (Solution implementation Roadmap) | 22
23 | Fulfill Virtual DaaS Product Team Adoption Plan (Solution implementation Roadmap) | 23
24 | Fulfill Virtual DaaS Product Team Adoption Plan (Solution implementation Roadmap (Duplicate)) | 24
25 | Implementation Plan on Cloud Integration of Virtual DaaS System (Solution implementation Roadmap) | 25
26 | Functional Cloud Integration of Virtual DaaS System (Solution implementation Roadmap) | 26
27 | Continue to Fulfill Virtual DaaS Product Team Adoption Plan (Solution implementation Roadmap) | 27
28 | Continued Fulfillment of Functional Self-Service Web Portal (Solution implementation Roadmap) | 28
29 | Improved Functional Cloud Integration of Virtual DaaS System (Solution implementation Roadmap) | 29
30 | Continued and Improved Fulfillment of Business Product Team Virtual DaaS Adoption Plan (Solution implementation Roadmap) | 30
31 | Optimized Functional Cloud Integration of Virtual DaaS System (Solution implementation Roadmap) | 31
32 | Continued and Optimized Fulfillment of Business Product Team Virtual DaaS Adoption Plan (Solution implementation Roadmap) | 32

## Product
Product | Product Line
Patent Center | Patent
Patent Exam Center | Patent
Patent Trial and Appeal Board (PTAB) Center | Patent
Patet Administrative Center | Patent
International Data Exchange | Patent
Patent Business & Content Management Services | Patent
Patent Data and Analytics | Patent
Patent Public API | Patent
Trademark Center | Trademark
Trademark Exam Center | Trademark
Trademark Trial and Appeal Board (TTAB) Center | Trademark
Trademark Exam International | Trademark
Trademark Data and Analytics | Trademark
Trademark Content Management Services | Trademark
Multimedia | Enterprise Business
Fee Management | Enterprise Business
Financial Management | Enterprise Business
Planning, Budgeting, and Governance | Enterprise Business
People Management | Enterprise Business
Property and Facility Management | Enterprise Business
Legal Tools | Enterprise Business
Data & Analytics | Enterprise Business
Dissemination and Assignments | Enterprise Business
End User Services | Enterprise Infrastructure
Platform Services | Enterprise Infrastructure
Infra/Hosting Services | Enterprise Infrastructure
Delivery Services | Enterprise Infrastructure
Security and Security Compliance Delivery Services | Enterprise Infrastructure
IT Managment Services | Enterprise Infrastructure
Emerging and Innovation | Enterprise Infrastructure

## Parms
Parameters
Annual Increase | 2%
Billable Hours Per Year | 1919
Weekday Hours Per Year | 2087
Federal Holidays | 11
PTO Days | 10
Paid Time Off Benefit | 8.05%
Workspace - PM Percentage Justification | Hours
PM Tasks | One_Time | Weekly | Monthly | FTE % | Hours | Task % | Prorated | Total | FTE %
Kick-Off | 80 |  |  | 0.5 | 80 | 8.338% | 8.601% | 930.1429 | 0.4847 | 96.94%
Weekly Status |  | 6 |  | 0.5 | 313.0714 | 32.63% | 33.66% |  |  | 100%
Monthly Status |  |  | 8 | 0.5 | 96 | 10.01% | 10.32%
Serve as Government point of contact and manage Contractor personnel |  | 4 |  | 0.5 | 208.7143 | 21.75% | 22.44%
Transition-Out | 40 |  | 4 | 0.5 | 88 | 9.171% | 9.461%
Define the Data as a Service Strategy, High-Level Roadmap for solution components & ROI/CBA | 40 | 0 |  | 0.5 | 40 | 4.169% | 4.3%
Identifying and interviewing core stakeholders involved in end-to-end processes. |  | 0 |  | 0.5 | 0 | 0% | 0%
Reviewing the current process interactions, configuration of environments & data, support team alignment, KPI & artifacts to interdependencies across processes |  | 0 |  | 0.5 | 0 | 0% | 0%
Identifying the opportunities for improvements along with recommendations for Planning and Solution Design phase. |  | 2 |  | 0.5 | 104.3571 | 10.88% | 11.22%
|  | 0 |  | 0.5 | 0 | 0% | 0%
Weekly Status |  | 6 |  | 0.5 | 313.0714 | 32.63% | 39.42% | 794.1429 | 0.41383 | 82.77%
Monthly Status |  |  | 8 | 0.5 | 96 | 10.01% | 12.09% |  |  | 100%
Serve as Government point of contact and manage Contractor personnel |  | 4 |  | 0.5 | 208.7143 | 21.75% | 26.28%
Transition-Out |  |  | 4 | 0.5 | 48 | 5.003% | 6.044%
Define the Data as a Service Strategy, High-Level Roadmap for solution components & ROI/CBA |  | 0 | 2 | 0.5 | 24 | 2.501% | 3.022%
Identifying and interviewing core stakeholders involved in end-to-end processes. |  | 0 |  | 0.5 | 0 | 0% | 0%
Reviewing the current process interactions, configuration of environments & data, support team alignment, KPI & artifacts to interdependencies across processes |  | 0 |  | 0.5 | 0 | 0% | 0%
Identifying the opportunities for improvements along with recommendations for Planning and Solution Design phase. |  | 2 |  | 0.5 | 104.3571 | 10.88% | 13.14%
|  | 0 |  | 0.5 | 0 | 0% | 0%
Weekly Status |  | 6 |  | 0.5 | 313.0714 | 32.63% | 36.65% | 854.1429 | 0.4451 | 89.02%
Monthly Status |  |  | 8 | 0.5 | 96 | 10.01% | 11.24% |  |  | 100%
Serve as Government point of contact and manage Contractor personnel |  | 4 |  | 0.5 | 208.7143 | 21.75% | 24.44%
Transition-Out | 60 |  | 4 | 0.5 | 108 | 11.26% | 12.64%
Define the Data as a Service Strategy, High-Level Roadmap for solution components & ROI/CBA |  | 0 | 2 | 0.5 | 24 | 2.501% | 2.81%
Identifying and interviewing core stakeholders involved in end-to-end processes. |  | 0 |  | 0.5 | 0 | 0% | 0%
Reviewing the current process interactions, configuration of environments & data, support team alignment, KPI & artifacts to interdependencies across processes |  | 0 |  | 0.5 | 0 | 0% | 0%
Identifying the opportunities for improvements along with recommendations for Planning and Solution Design phase. |  | 2 |  | 0.5 | 104.3571 | 10.88% | 12.22%
|  | 0 |  | 0.5 | 0 | 0% | 0%

## Codes
Key / Non-Key
Key
Non-Key
Product Lines
Patent
Trademark
Enterprise Business
Enterprise Infrastructure