## Project Gantt
Pacific Region MATOC - NASA Santa Susana Field Laboratory (SSFL) Ventura County - PANHES-22-P-0000 003493
PROJECT TITLE | Abatement and demolition services
PROJECT MANAGER | Eric Newman
COMPANY NAME | AllPhase
DATE | 2022-07-21
[7 empty] | PHASE ONE - Project Initiation and Coordination | [14 empty] | PHASE TWO - Project Preparation | [14 empty] | PHASE THREE - Demolition | [14 empty] | PHASE FOUR - Site cleanup & Close-out
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation and Coordination
1.1 | Project Management Plan |  | 2022-09-01 | 2022-09-08 | 7 | 0%
1.1.1 | PMP Revisions |  | 2022-09-08 | 2022-09-13 | 5 | 0%
1.2 | Project Kickoff Meeting/NTP Date |  | 2022-09-14 | 2022-09-15 | 1 | 0%
1.3 | Staffing and Resource Deployment |  | 2022-09-15 | 2022-09-21 | 6 | 0%
1.4 | Risk Management, Quality Control Plan Update |  | 2022-09-14 | 2022-09-21 | 7 | 0%
1.5 | Mobilization Date
2 | Project Preparation
2.1 | Stage 1: Hazardous materials diagnosis |  |  |  |  | 0%
2.2 | Stage 2: Documentation of the demolition |  |  |  |  | 0%
2.3 | Stage 3: Clearing the building |  |  |  |  | 0%
2.4 | Stage 4: Building decontamination |  |  |  |  | 0%
3 | Stage 5: Building demolition
3.1 | Site walk, set up site office |  |  |  |  | 0%
3.2 | Blueprint and PMP review with team |  |  |  |  | 0%
3.2.1 | Equipment procurement and staging |  |  |  |  | 0%
3.2.2 | Receive and secure vehicles/equipment |  |  |  |  | 0%
3.3 | Block off area and establish access points |  |  |  |  | 0%
3.3.1 | Review safety procedures with crew |  |  |  |  | 0%
3.4 | Preliminary material stripping (electrical, plumbing, etc.) |  |  |  |  | 0%
3.5 | Demolish structure |  |  |  |  | 0%
3.6 | Waste material sorting |  |  |  |  | 0%
3.7 | Foundation excavation |  |  |  |  | 0%
4 | Stage 6: Site cleanup
4.1 | Waste material transport off-site |  |  |  |  | 0%
4.2 | Remove temporary fencing and signage |  |  |  |  | 0%
4.3 | Demobilize on-site equipment and office |  |  |  |  | 0%
4.4 | Final inspection and walk-through |  |  |  |  | 0%
5 | Project Performance / Monitoring
5.1 | Project Objectives, Status & Tracking KPIs |  |  |  |  | 0%
5.2 | Quality Monitoring & Deliverables |  |  |  |  | 0%
5.3 | Levels of Effort and Cost Tracking |  |  |  |  | 0%
5.4 | Project Performance Update - reconcile labor, materials budgeting |  |  |  |  | 0%