## Base Bid
COST SUMMARY SPREADSHEET
Demolition at |  | Milan Army Ammunition Plant, TN | FY22
| Project Manager | Harris, Tina L
| Program Manager | Newman, Eric
| Superintendent | Perez, Jorge
| Quality Control Manager | Soto, Alberto
| Safety Officer | Soto, Alberto
| Clerk | Osorio, Clementina D
| Location | Milan Army Ammunition Plant, TN
| Total Contract Duration | 411 | WD
| Pre Mobilization | 161
| Mobilization/Abatement/Demolition | 75
| Site Restoration/Demobilization | 30
| Category | # Proposed
| Program Manager | 1
| Principal | 1
| Project Manager | 1
| Safety Officer | 1
| Superintendent | 1
| Operator(s) | 2
| Demolition Laborers | 2
| Asbestos/Lead/HazMat Abatement | 12
| Backfill/cy | 1851
| Topsoil/cy | 1481
| Seed & Straw/sf | 120000

## Demo_Takeoff (hidden)
BID ITEM | FACNO | NOTES | DESCRIPTION | Pictures | Pictures | PUM | PUM QTY | Duration (Demo) | Duration (Site Rest) | Conc | Trash | 80#clas | 100# | Loader | Skidsteer | Attach (Hammer) | Shear | Trucks (Loads) | Water Trucks | # of Stories | ACM | LBP | ORM | Type of Building | Other Structures Onsite | Foundation | Basement/Crawlspace | Site Restoration | General Building Condition | Operator | Labor | Asbestos | LBP | ORM | Demo Sub Unit Cost | Demo Sub Cost | Salvage Credit
[10 empty] | 20 YD | 100yd |  |  | 3 CY | [23 empty] | Site Rest Cal
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | [12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | [12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
|  |  | TOTAL |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 0 | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | [12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
|  |  | TOTAL |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 0 | #REF!
#REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | [12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
|  |  | TOTAL |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 0 | #REF!
|  |  | Grand Total |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 0 | #REF!
5.7105
862
#REF!
#REF!

## ACM
DESCRIPTION | PUM | PUM QTY | ACM ABATEMENT | [8 empty] | LBP ABATEMENT | ORM Abatement (PCBs, Mercury, etc.)
|  |  | Light Fixture Gaskets | Flooring, Mastic & Cove Base | Doors & Windows Components | Roof Sealers | Roofing | Sealers, Caulk, Putty on Walls and Panels | Pipe | Transite Panel | Boilers & Duct | Painted Surfaces containing RCRA 8 Metals and/or PCBs
Bldg. #: E0001; Bldg. #: E0003; Bldg. #: E0005; Bldg. #: E0008; Bldg. #: E0009 | SF | 10993 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
Bldg. #: E0012; Bldg. #: E0013 | SF | 886 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Bldg. #: E0041; Bldg. #: E0042; Bldg. #: E0043; Bldg. #: E0047; Bldg. #: E0048; Bldg. #: E0049; Bldg. #: E0044; Bldg. #: E0046 | SF | 15426 | 1 | 1 | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 2 | 1
Bldg. #: E0852 | SF | 13743 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
Bldg. #: F0001; Bldg. #: F0005 | SF | 108 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Bldg. #: F0010; Bldg. #: F0018; Bldg. #: F0019 | SF | 12874 | 1 | 0 | 2 | 1 | 1 | 1 | 1 | 2 | 0 | 2 | 2
Bldg. #: F0020; Bldg. #: F0021 | SF | 8894 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2
Bldg. #: F0052; Bldg. #: F0053 | SF | 12737 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 1
Bldg. #: F0173; Bldg. #: F0852 | SF | 5575 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1
101891
KEY = Degree of Difficulty
|  |  | Easy | Medium | Hard

## Demolition
DESCRIPTION | UM | QTY | STRUCTURES
|  |  | CMU/Brick Structure | Metal Structure | Sidewalks | Wood Structure
Bldg. #: E0001; Bldg. #: E0003; Bldg. #: E0005; Bldg. #: E0008; Bldg. #: E0009 | SF | 10993 | 2 | 1 | 1 | 1
Bldg. #: E0012; Bldg. #: E0013 | SF | 886 | 1 | 0 | 0 | 0
Bldg. #: E0041; Bldg. #: E0042; Bldg. #: E0043; Bldg. #: E0047; Bldg. #: E0048; Bldg. #: E0049; Bldg. #: E0044; Bldg. #: E0046 | SF | 15426 | 1 | 2 | 0 | 0
Bldg. #: E0852 | SF | 13743 | 0 | 2 | 0 | 0
Bldg. #: F0001; Bldg. #: F0005 | SF | 108 | 0 | 1 | 0 | 0
Bldg. #: F0010; Bldg. #: F0018; Bldg. #: F0019 | SF | 12874 | 2 | 0 | 0 | 0
Bldg. #: F0020; Bldg. #: F0021 | SF | 8894 | 2 | 0 | 0 | 0
Bldg. #: F0052; Bldg. #: F0053 | SF | 12737 | 0 | 2 | 0 | 0
Bldg. #: F0173; Bldg. #: F0852 | SF | 5575 | 0 | 1 | 0 | 0
KEY = Degree of Difficulty
|  |  | Easy | Medium | Hard

## HAZMAT
ASBESTOS ABATEMENT-MAN POWER DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Officer | Super | Laborer | PCM
Sampling
| HR | HR | HR | HR | HR | HR
Bldg. #: E0001; Bldg. #: E0003; Bldg. #: E0005; Bldg. #: E0008; Bldg. #: E0009 | 2 | 6.5 | 1.25 | 9 | 91 | 80
Bldg. #: E0012; Bldg. #: E0013 | 0.75 | 2.5 | 0.5 | 4 | 28 | 32
Bldg. #: E0041; Bldg. #: E0042; Bldg. #: E0043; Bldg. #: E0047; Bldg. #: E0048; Bldg. #: E0049; Bldg. #: E0044; Bldg. #: E0046 | 10.25 | 50.25 | 2.75 | 67 | 735 | 703
Bldg. E0852 | 1 | 8 | 0.25 | 10 | 114 | 4
Bldg. #: F0001; Bldg. #: F0005 | 0.5 | 1 | 0.5 | 2 | 14 | 13
Bldg. #: F0010; Bldg. #: F0018; Bldg. #: F0019 | 4.25 | 23 | 1 | 31 | 341 | 224
Bldg. #: F0020; Bldg. #: F0021 | 2.25 | 13.5 | 0.75 | 19 | 205 | 85
Bldg. #: F0052; Bldg. #: F0053 | 9 | 50 | 1.25 | 67 | 747 | 909
Bldg. #: F0173; Bldg. #: F0852 | 3.25 | 19.25 | 0.75 | 26 | 287 | 393

## DEMO & SITE
DEMOLITION & SITE RESTORATION-MAN POWER & EQUIPMENT DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Officer | Super | Operators | Laborer | Exc/UP | Skid Steer | Attach (Hammer) | Truck | Water Truck | TCLP
[7 empty] | 80#clas |  |  |  |  | Sampling
| HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | EA
Bldg. #: E0001; Bldg. #: E0003; Bldg. #: E0005; Bldg. #: E0008; Bldg. #: E0009 | 5 | 23.5 | 1.5 | 423 | 252 | 252 | 32.5 | 32.5 | 0 | 512 | 190 | 5
Bldg. #: E0012; Bldg. #: E0013 | 1.25 | 4 | 0.5 | 71 | 42 | 42 | 6 | 6 | 0 | 112 | 32 | 2
Bldg. #: E0041; Bldg. #: E0042; Bldg. #: E0043; Bldg. #: E0047; Bldg. #: E0048; Bldg. #: E0049; Bldg. #: E0044; Bldg. #: E0046 | 7.5 | 33 | 2.25 | 615 | 365 | 365 | 41 | 41 | 7 | 704 | 276 | 8
Bldg. E0852 | 4 | 21 | 0.5 | 385 | 229 | 229 | 29 | 29 | 0 | 192 | 172 | 1
Bldg. #: F0001; Bldg. #: F0005 | 0.5 | 2 | 0.5 | 20 | 12 | 12 | 2 | 2 | 0 | 32 | 10 | 2
Bldg. #: F0010; Bldg. #: F0018; Bldg. #: F0019 | 5.25 | 25 | 1 | 455 | 270 | 270 | 34 | 34 | 0 | 280 | 204 | 3
Bldg. #: F0020; Bldg. #: F0021 | 3.5 | 17 | 0.75 | 313 | 186 | 186 | 24 | 24 | 0 | 208 | 140 | 2
Bldg. #: F0052; Bldg. #: F0053 | 4 | 20 | 0.75 | 370 | 220 | 220 | 28 | 28 | 0 | 216 | 165 | 2
Bldg. #: F0173; Bldg. #: F0852 | 1.25 | 8 | 0.5 | 147 | 86 | 86 | 11 | 11 | 0 | 136 | 65 | 2

## Form
Waste Management Report (Estimated)
Contract Number: | [5 empty] | Gov't Inspector: |  | tbd
Contractor: |  | All Phase Services, Inc. |  |  |  | Project # Title: |  | Demolition at Milan Army Ammunition Plant, TN FY22
Contractor POC: |  | Carlos Martins |  |  |  | Date:
Phone No: |  | 561-756-6647
I. Sanitary Landfill Waste | [5 empty] | II. Inert Landfill Disposal
Quantity (tons): |  | n/a |  |  |  | Quantity (tons):
Landfill Site: | [5 empty] | Landfill Site:
Tip fee/ton ($/ton): | [5 empty] | * Total cost of disposal ($):
* Total cost of disposal ($): | [5 empty] | * Total cost/ton ($/ton):
* Total cost/ton ($/ton):
III. Alternatives to Landfilling (Recycling Strongly Encouraged) | [5 empty] | Total tonnage of all material
Type Of Material | Original Estimated (pounds) | Actual Quantity (pounds) | % diversion from total | Destination | * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Comparison Cost (+) / Savings (-)
Asphalt |  |  |  | Recycle
C&D | 1200000 |  |  | Landfill
Concrete | 6600000 |  |  | Crusher/Recycle
Metals - All Types | 120000 |  |  | Recycle |  |  |  |  | -12000
Total | 7920000
IV. Total net cost (+) or savings (-) from all alternatives to landfilling all project waste | [8 empty] | -12000
V. Means of keeping recyclables free of contamination
All similar materials will be grouped together based on the requirements of the recycling center. All dissimilar materials will be kept in separate containers/bins in order to avoid contamination.
VI. Meetings to be held to address waste management
At regularly scheduled job site coordination/progress meetings and at job safety meetings, waste management requirements will be discussed to clarify any confusion with craftspeople.
* Optional
Asphalt | 450000 | 462000 | 1.118%
Land Fill |  |  | 5.804%
Concrete | 30000000 | 37000000 | 89.56%
Metals - All Types | 1200000 | 1445938 | 3.5%
Electric Cable | 10000 | 7580 | 0.01835%
| * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Savings from Diversion | 0
Concrete | 32482.8532 | 333000 | -300517.1468 | 370000 | -670517.1468 | 670517.1468
Asphalt | 2737.7778 | 924 | 1813.7778 | 4620 | -2806.2222 | 673323.369
Metals - All Types | 59600 | 72420 | -12820 | 14459.38 | -27279.38 | 700602.749
Electric Cable | 2274 | 6064 | -3790 | 75.8 | -3865.8 | 704468.549
Asphalt | 0 | 0% | 0
C&D (Landfill) | 1200000 | 15% | 600
Concrete (Recycled) | 6600000 | 83% | 3300
Metals - All Types (Recycled) | 120000 | 2% | 60
| 7920000 | 85%