## Base Bid
COST SUMMARY SPREADSHEET
Demolition at |  | Rio Puerto Nuevo, San Juan, Puerto Rico | FY22
| PWS | 2022-08-24
| Proposal Due Date | 2022-09-02
| Project Manager | Lind, Eric
| Program Manager | Newman, Eric
| Superintendent | Luyando, William
| Quality Control Manager | Soto, Alberto
| Safety Officer | Soto, Alberto
| Clerk | Osorio, Clementina D
| Location | Rio Puerto Nuevo, San Juan, Puerto Rico
| Total Contract Duration | 245 | WD
| Pre Mobilization | 60
| Mobilization/Abatement/Demolition | 30
| Site Restoration/Demobilization | 10
| Days for Closeout Documents | 145
Category | # Proposed
Program Manager | 1
Principal
Project Manager | 1
Admin | 1
Safety Officer/QC Manager | 1
Superintendent | 1
Operator(s) | 1
Demolition Laborers | 2
Backfill/cy | 600
Topsoil/cy | 506
Seed & Straw/psf | 41000

## Demolition
FACNO | DESCRIPTION | UM | QTY | STRUCTURES
|  |  |  | Basement/Crawlspace | Conc Pads | SOG
300 | 267 25th NE Street | SF | 1705 | 0 | 1 | 1
301 | 269 25th NE Street | SF | 1774 | 0 | 1 | 1
303 | 273 25th NE Street | SF | 1849 | 0 | 1 | 1
304 | 275 25th NE Street | SF | 1042 | 0 | 1 | 1
305 | 277 25th NE Street | SF | 1164 | 0 | 1 | 1
306 | 279 25th NE Street | SF | 809 | 0 | 1 | 1
308 | 30125th NE Street | SF | 1426 | 0 | 0 | 1
310 | 305 25th NE Street | SF | 696 | 0 | 0 | 1
311 | 307 25th NE Street | SF | 1388 | 0 | 0 | 1
312 | 309 25th NE Street | SF | 808 | 0 | 0 | 1
313 | 31125th NE Street | SF | 2049 | 0 | 0 | 1
314 | 313 25th NE Street | SF | 1645 | 0 | 0 | 1
315 | 315 25th NE Street | SF | 995 | 0 | 0 | 1
316 | 317 25th NE Street | SF | 1029 | 0 | 0 | 1
KEY = Degree of Difficulty
|  |  |  | Easy | Medium | Hard

## DEMO & SITE
DEMOLITION & SITE RESTORATION-MAN POWER & EQUIPMENT DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Officer | Super | Operators | Laborer | Exc/UP | Dozer | Skid Steer | Attach (Hammer) | Shear | Truck | Water Truck | TCLP
[7 empty] | 80#clas | 3 CY | [5 empty] | Sampling
| HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | EA
Bldg. 300; 267 25th NE Street | 11 | 38 | 30 | 51 | 30 | 30 | 7 | 7 | 7 | 0 | 0 | 72 | 42 | 1
Bldg. 301; 269 25th NE Street | 12 | 39 | 31 | 53 | 31 | 31 | 7 | 7 | 7 | 0 | 0 | 72 | 44 | 1
Bldg. 303; 273 25th NE Street | 12 | 41 | 32 | 55 | 32 | 32 | 7 | 7 | 7 | 0 | 0 | 72 | 45 | 1
Bldg. 304; 275 25th NE Street | 7 | 23 | 18 | 31 | 18 | 18 | 4 | 4 | 4 | 0 | 0 | 52 | 25 | 1
Bldg. 305; 277 25th NE Street | 8 | 26 | 20 | 35 | 20 | 20 | 5 | 5 | 5 | 0 | 0 | 52 | 28 | 1
Bldg. 306; 279 25th NE Street | 5 | 18 | 14 | 24 | 14 | 14 | 3 | 3 | 3 | 0 | 0 | 36 | 20 | 1
Bldg. 308; 30125th NE Street | 10 | 32 | 25 | 43 | 25 | 25 | 6 | 6 | 6 | 0 | 0 | 72 | 35 | 1
Bldg. 310; 305 25th NE Street | 5 | 15 | 12 | 21 | 12 | 12 | 3 | 3 | 3 | 0 | 0 | 36 | 17 | 1
Bldg. 311; 307 25th NE Street | 9 | 31 | 24 | 42 | 24 | 24 | 6 | 6 | 6 | 0 | 0 | 64 | 34 | 1
Bldg. 312; 309 25th NE Street | 5 | 18 | 14 | 24 | 14 | 14 | 3 | 3 | 0 | 0 | 0 | 36 | 20 | 1
Bldg. 313; 31125th NE Street | 14 | 45 | 36 | 61 | 36 | 36 | 8 | 8 | 8 | 0 | 0 | 72 | 51 | 1
Bldg. 314; 313 25th NE Street | 11 | 36 | 29 | 49 | 29 | 29 | 7 | 7 | 7 | 0 | 0 | 72 | 41 | 1
Bldg. 315; 315 25th NE Street | 7 | 22 | 17 | 30 | 17 | 17 | 4 | 4 | 4 | 0 | 0 | 48 | 24 | 1
Bldg. 316; 317 25th NE Street | 7 | 23 | 18 | 31 | 18 | 18 | 4 | 4 | 4 | 0 | 0 | 48 | 25 | 1

## Form
Waste Management Report (Estimated)
Contract Number: | [5 empty] | Gov't Inspector: |  | tbd
Contractor: |  | All Phase Services, Inc. |  |  |  | Project # Title: |  | Demolition at Rio Puerto Nuevo, San Juan, Puerto Rico FY22
Contractor POC: |  | Carlos Martins |  |  |  | Date:
Phone No: |  | 561/620-8222
I. Sanitary Landfill Waste | [5 empty] | II. Inert Landfill Disposal
Quantity (tons): |  | n/a |  |  |  | Quantity (tons):
Landfill Site: | [5 empty] | Landfill Site:
Tip fee/ton ($/ton): | [5 empty] | * Total cost of disposal ($):
* Total cost of disposal ($): | [5 empty] | * Total cost/ton ($/ton):
* Total cost/ton ($/ton):
III. Alternatives to Landfilling (Recycling Strongly Encouraged) | [5 empty] | Total tonnage of all material
Type Of Material | Original Estimated (pounds) | Actual Quantity (pounds) | % diversion from total | Destination | * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Comparison Cost (+) / Savings (-)
Asphalt |  |  |  | Recycle
C&D | 1110000 |  |  | Landfill
Concrete | 8684000 |  |  | Crusher/Recycle
Metals - All Types | 112000 |  |  | Recycle |  |  |  |  | -11200
Total | 9906000
IV. Total net cost (+) or savings (-) from all alternatives to landfilling all project waste | [8 empty] | -11200
V. Means of keeping recyclables free of contamination
All similar materials will be grouped together based on the requirements of the recycling center. All dissimilar materials will be kept in separate containers/bins in order to avoid contamination.
VI. Meetings to be held to address waste management
At regularly scheduled job site coordination/progress meetings and at job safety meetings, waste management requirements will be discussed to clarify any confusion with craftspeople.
* Optional
Asphalt | 450000 | 462000 | 1.118%
Land Fill |  |  | 5.804%
Concrete | 30000000 | 37000000 | 89.56%
Metals - All Types | 1200000 | 1445938 | 3.5%
Electric Cable | 10000 | 7580 | 0.01835%
| * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Savings from Diversion | 0
Concrete | 32482.8532 | 333000 | -300517.1468 | 370000 | -670517.1468 | 670517.1468
Asphalt | 2737.7778 | 924 | 1813.7778 | 4620 | -2806.2222 | 673323.369
Metals - All Types | 59600 | 72420 | -12820 | 14459.38 | -27279.38 | 700602.749
Electric Cable | 2274 | 6064 | -3790 | 75.8 | -3865.8 | 704468.549
Asphalt | 0 | 0% | 0
C&D (Landfill) | 1110000 | 10% | 555
Concrete (Recycled) | 8684000 | 88% | 4342
Metals - All Types (Recycled) | 112000 | 2% | 56
| 9906000 | 90%