## Base Bid
Demolition at |  | Fort Benning, GA | FY22
| PWS | 2022-08-02
| Proposal Due Date | 2022-08-31
| Project Manager | Harris, Tina L
| Program Manager | Newman, Eric
| Superintendent | Gauthier, Robert A
| Quality Control Manager | Jorge Perez
| Safety Officer | Williams, Brett
| Clerk | Osorio, Clementina D
| Location | Fort Benning, GA
| Total Contract Duration | 461 | WD
| Pre Mobilization | 96
| Mobilization/Abatement/Demolition | 200
| Site Restoration/Demobilization | 20
| Days for Closeout Documents | 145
Category | # Proposed
Site CQC Manager | 1
Safety Officer | 1
Superintendent | 1
Operator(s) | 4
Demolition Laborers | 6
Asbestos/Lead/HazMat Abatement | 1+31
Backfill/cy | 42000
Topsoil/cy | 3333
Seed & Straw/sf | 270000

## ACM
FACNO | DESCRIPTION | PUM | PUM QTY |  | ACM ABATEMENT | [17 empty] | LBP ABATEMENT | [11 empty] | Other Regulated Material Abatement (PCBs, Mercury, etc.)
[5 empty] | Transite | VAT/Mastic | Residual Mastic | Wall Mastic | Sink Undercoat | Seam Sealant | Elbow Insulation | Mastic on Pipe | Door Insulation | Table Tops | Window Glazing/Gaskets | Wiring | Flashing | Door Frame Caulking | Ceramic Tile and Grout | Pipe Insulation | Roofing and Flashing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9200 | Main Hospital Building | SF | 393077 |  | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | [17 empty] | 3
9201 | Chiller Building | SF | 1721 | [14 empty] | 1 | [16 empty] | 1
9202 | Boiler House | SF | 6590 | [5 empty] | 1 |  | 1 | 1 |  |  | 1 |  |  |  | 1 | 2 | 2 | [13 empty] | 2
9208 | Admin Building | SF | 2442
9211 | Officce Trailers | SF | 8856 | [31 empty] | 2
412686
KEY = Degree of Difficulty
[5 empty] | Easy | Medium | Hard
#REF!

## Demolition
FACNO | DESCRIPTION | UM | QTY | STRUCTURES
|  |  |  | Basement/Crawlspace | BBQ Pits | Chimney | CMU/Brick Structure | Conc Pads | Conc Structure | Fence | Fuel/Oil Tank | Metal Structure | Pier & Beam | Piles | Playground | Poles | Ramps | Asphalt | Rock Removal | Sheds/Shacks | AST | Sidewalks | SOG | Utilities | Tower | Water Tower | Wood Structure | UST
9200 | Main Hospital Building | SF | 393077 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9201 | Chiller Building | SF | 1721 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
9202 | Boiler House | SF | 6590 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
9208 | Admin Building | SF | 2442 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
9211 | Officce Trailers | SF | 8856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY = Degree of Difficulty
|  |  |  | Easy |  |  | Medium |  | Hard

## HAZMAT
ASBESTOS ABATEMENT-MAN POWER DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Officer | Supervisor | Laborer | PCM
Sampling
| HR | HR | HR | HR | HR | HR
Bldg. 9200 | 175 | 616 | 341 | 694 | 21572 | 15407
Bldg. 9201 | 0 | 1 | 0 | 2 | 48 | 7
Bldg. 9202 | 5 | 18 | 0 | 20 | 613 | 444
Bldg. 9208 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 9211 | 0 | 0 | 0 | 0 | 0 | 0

## DEMO & SITE
DEMOLITION & SITE RESTORATION-MAN POWER & EQUIPMENT DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Officer | Super | Operators | Laborer | Exc/UP | Exc/B&T | Loader | Skid Steer | Attach (Universal Processor) | HighReach | Onsite Crusher | Truck | Water Truck | TCLP
[7 empty] | 80#clas | 100# | 3 CY | [6 empty] | Sampling
| HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | EA
Bldg. 9200 | 264 | 927 | 512 | 2767 | 6595 | 9893 | 822 | 822 | 411 | 822 | 822 | 308 | 411 | 11200 | 2467 | 37
Bldg. 9201 | 2 | 8 | 4 | 24 | 58 | 87 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 320 | 22 | 1
Bldg. 9202 | 7 | 23 | 13 | 70 | 166 | 249 | 10 | 0 | 10 | 10 | 0 | 8 | 10 | 416 | 62 | 1
Bldg. 9208 | 3 | 10 | 6 | 30 | 72 | 108 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 96 | 27 | 1
Bldg. 9211 | 6 | 21 | 12 | 62 | 149 | 223 | 9 | 0 | 0 | 9 | 0 | 9 | 9 | 112 | 56 | 1

## Form
Waste Management Report (Estimated)
Contract Number: | [5 empty] | Gov't Inspector: |  | tbd
Contractor: |  | All Phase Services, Inc. |  |  |  | Project # Title: |  | Demolition at Fort Benning, GA FY22
Contractor POC: |  | Carlos Martins |  |  |  | Date:
Phone No: |  | 561-756-6647
I. Sanitary Landfill Waste | [5 empty] | II. Inert Landfill Disposal
Quantity (tons): |  | n/a |  |  |  | Quantity (tons):
Landfill Site: | [5 empty] | Landfill Site:
Tip fee/ton ($/ton): | [5 empty] | * Total cost of disposal ($):
* Total cost of disposal ($): | [5 empty] | * Total cost/ton ($/ton):
* Total cost/ton ($/ton):
III. Alternatives to Landfilling (Recycling Strongly Encouraged) | [5 empty] | Total tonnage of all material
Type Of Material | Original Estimated (pounds) | Actual Quantity (pounds) | % diversion from total | Destination | * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Comparison Cost (+) / Savings (-)
Asphalt |  |  |  | Recycle
C&D | 8000000 |  |  | Landfill
Concrete | 79200000 |  |  | Crusher/Recycle
Metals - All Types | 3210000 |  |  | Recycle |  |  |  |  | -321000
Total | 90410000
IV. Total net cost (+) or savings (-) from all alternatives to landfilling all project waste | [8 empty] | -321000
V. Means of keeping recyclables free of contamination
All similar materials will be grouped together based on the requirements of the recycling center. All dissimilar materials will be kept in separate containers/bins in order to avoid contamination.
VI. Meetings to be held to address waste management
At regularly scheduled job site coordination/progress meetings and at job safety meetings, waste management requirements will be discussed to clarify any confusion with craftspeople.
* Optional
Asphalt | 450000 | 462000 | 1.118%
Land Fill |  |  | 5.804%
Concrete | 30000000 | 37000000 | 89.56%
Metals - All Types | 1200000 | 1445938 | 3.5%
Electric Cable | 10000 | 7580 | 0.01835%
| * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Savings from Diversion | 0
Concrete | 32482.8532 | 333000 | -300517.1468 | 370000 | -670517.1468 | 670517.1468
Asphalt | 2737.7778 | 924 | 1813.7778 | 4620 | -2806.2222 | 673323.369
Metals - All Types | 59600 | 72420 | -12820 | 14459.38 | -27279.38 | 700602.749
Electric Cable | 2274 | 6064 | -3790 | 75.8 | -3865.8 | 704468.549
Asphalt | 0 | 0% | 0
C&D (Landfill) | 8000000 | 8% | 4000
Concrete (Recycled) | 79200000 | 88% | 39600
Metals - All Types (Recycled) | 3210000 | 4% | 1605
| 90410000 | 92%