## Base Bid
COST SUMMARY SPREADSHEET
Demolition at |  | Joint Base San Antonio, Camp Bullis, TX | FY22
| PWS | 2022-09-16
| Proposal Due Date | 2022-09-23
| Project Manager | Fults, Brandon D
| Program Manager | Newman, Eric
| Superintendent | Williams, Brett
| Quality Control Manager | Quigley, Khalilah A
| Safety Officer | Quigley, Khalilah A
| Clerk | Osorio, Clementina D
| Location | Joint Base San Antonio, Camp Bullis, TX
| Total Contract Duration | 266 | WD
| Pre Mobilization | 96
| Mobilization/Abatement/Demolition | 30
| Site Restoration/Demobilization | 10
| Days for Closeout Documents | 130
| Depth of Foundation to be removed |  | Feet
| Depth of Topsoil to be installed |  | Inches
| Is salvage property of Govt | No
| Compaction required | 90%
| Category | # Proposed
Professional Labor
| Site CQC Manager | 1
| Superintendent | 1
| Operator(s) | 1
| Demolition Laborers | 1
| Asbestos/Lead/HazMat Abatement | 1 Super+6 Workers
| Topsoil/cy | 90
| Seed & Straw/psf | 8000

## ACM
FACNO | DESCRIPTION | PUM | PUM QTY | ACM ABATEMENT | [5 empty] | ORM (PCBs, Mercury, etc.)
|  |  |  | Wall Tile | Roof Penetration | Drywall | VAT/Mastic | Entire Condemned | Roof Vents
6202 | Admin OFC Non-AF | SF | 1479 | 1 | 1 |  |  |  |  | 1
6204 | Admin OFC Non-AF | SF | 1454 |  | 1 | 1 |  |  |  | 1
5110 | Warehouse | SF | 710 |  | 1 |  | 1 |  |  | 1
5122 | Tech Training Classroom | SF | 3606 |  |  |  |  | 3
5123 | Tech Training Classroom | SF | 2594 |  |  |  |  | 3
5124 | Dining Facility | SF | 4392 | [5 empty] | 1 | 1
5288 | Camp Troop | SF | 522 | [6 empty] | 1
5289 | Camp Troop | SF | 522 | [6 empty] | 1
5290 | Camp Troop | SF | 522 | [6 empty] | 1
5291 | Camp Troop | SF | 522 | [6 empty] | 1
5292 | Camp Troop | SF | 522 | [6 empty] | 1
5293 | Camp Troop | SF | 522 | [6 empty] | 1
5294 | Camp Troop | SF | 522 | [6 empty] | 1
17889
KEY = Degree of Difficulty
|  |  |  | Easy | Medium | Hard

## Demolition
FACNO | DESCRIPTION | UM | QTY | STRUCTURES
|  |  |  | Basement/Crawlspace | Pier & Beam | Wood Structure | UST
6202 | Admin OFC Non-AF | SF | 1479 | 1 | 0 | 1 | 0
6204 | Admin OFC Non-AF | SF | 1454 | 1 | 0 | 1 | 0
5110 | Warehouse | SF | 710 | 1 | 0 | 1 | 0
5122 | Tech Training Classroom | SF | 3606 | 0 | 0 | 3 | 0
5123 | Tech Training Classroom | SF | 2594 | 0 | 0 | 3 | 0
5124 | Dining Facility | SF | 4392 | 1 | 0 | 2 | 0
5288 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
5289 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
5290 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
5291 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
5292 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
5293 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
5294 | Camp Troop | SF | 522 | 0 | 0 | 1 | 0
KEY = Degree of Difficulty
|  |  |  | Easy | Medium | Hard

## HAZMAT
ASBESTOS ABATEMENT-MAN POWER DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Engineer | Super | Laborer | PCM
Sampling
| HR | HR | HR | HR | HR | HR
Bldg. 6202 | 0.25 | 0.25 | 0.25 | 13 | 78 | 11
Bldg. 6204 | 0.25 | 0 | 0 | 13 | 77 | 11
Bldg. 5110 | 0.25 | 0.25 | 0.25 | 10 | 56 | 8
Bldg. 5122 | 1 | 1 | 1 | 31 | 190 | 27
Bldg. 5123 | 0.5 | 1 | 1 | 23 | 136 | 20
Bldg. 5124 | 0.25 | 0.25 | 0.25 | 38 | 231 | 33
Bldg. 5288 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 5289 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 5290 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 5291 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 5292 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 5293 | 0 | 0 | 0 | 0 | 0 | 0
Bldg. 5294 | 0 | 0 | 0 | 0 | 0 | 0

## DEMO & SITE
DEMOLITION & SITE RESTORATION-MAN POWER & EQUIPMENT DISTRIBUTION
Bldg. No | Program Manager | Admin | Safety Engineer | Super | Operators | Laborer | Exc/UP | Skid Steer | Truck | Water Truck | TCLP
[7 empty] | 40# Rubber Tire |  |  |  | Sampling
| HR | HR | HR | HR | HR | HR | HR | HR | HR | HR | EA
Bldg. 6202 | 4 | 6 | 6 | 29 | 23 | 23 | 23 | 16 | 40 | 16 | 1
Bldg. 6204 | 4 | 6 | 6 | 29 | 23 | 23 | 23 | 16 | 40 | 16 | 1
Bldg. 5110 | 3 | 4 | 4 | 22 | 17 | 17 | 17 | 8 | 16 | 8 | 1
Bldg. 5122 | 9 | 14 | 14 | 70 | 56 | 56 | 56 | 16 | 80 | 16 | 1
Bldg. 5123 | 6 | 10 | 10 | 50 | 40 | 40 | 40 | 16 | 64 | 16 | 1
Bldg. 5124 | 11 | 17 | 17 | 88 | 70 | 70 | 70 | 16 | 104 | 16 | 1
Bldg. 5288 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1
Bldg. 5289 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1
Bldg. 5290 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1
Bldg. 5291 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1
Bldg. 5292 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1
Bldg. 5293 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1
Bldg. 5294 | 2 | 3 | 3 | 16 | 13 | 13 | 13 | 8 | 16 | 8 | 1

## Form
Waste Management Report (Estimated)
Contract Number: | [5 empty] | Gov't Inspector: |  | tbd
Contractor: |  | All Phase Services, Inc. |  |  |  | Project # Title: |  | Demolition at Joint Base San Antonio, Camp Bullis, TX FY22
Contractor POC: |  | Carlos |  |  |  | Date:
Phone No: |  | (561) 620-8222
I. Sanitary Landfill Waste | [5 empty] | II. Inert Landfill Disposal
Quantity (tons): |  | n/a |  |  |  | Quantity (tons):
Landfill Site: | [5 empty] | Landfill Site:
Tip fee/ton ($/ton): | [5 empty] | * Total cost of disposal ($):
* Total cost of disposal ($): | [5 empty] | * Total cost/ton ($/ton):
* Total cost/ton ($/ton):
III. Alternatives to Landfilling (Recycling Strongly Encouraged) | [5 empty] | Total tonnage of all material
Type Of Material | Original Estimated (pounds) | Actual Quantity (pounds) | % diversion from total | Destination | * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Comparison Cost (+) / Savings (-)
Asphalt |  |  |  | Recycle
C&D | 960000 |  |  | Landfill
Concrete | 0 |  |  | Crusher/Recycle
Metals - All Types | 4000 |  |  | Recycle |  |  |  |  | -400
Total | 964000
IV. Total net cost (+) or savings (-) from all alternatives to landfilling all project waste | [8 empty] | -400
V. Means of keeping recyclables free of contamination
All similar materials will be grouped together based on the requirements of the recycling center. All dissimilar materials will be kept in separate containers/bins in order to avoid contamination.
VI. Meetings to be held to address waste management
At regularly scheduled job site coordination/progress meetings and at job safety meetings, waste management requirements will be discussed to clarify any confusion with craftspeople.
* Optional
Asphalt | 450000 | 462000 | 1.118%
Land Fill |  |  | 5.804%
Concrete | 30000000 | 37000000 | 89.56%
Metals - All Types | 1200000 | 1445938 | 3.5%
Electric Cable | 10000 | 7580 | 0.01835%
| * Handling and Transportation Cost ($) | * Expected Revenue and Tip Fee Earnings ($) | * Net Cost ($) | * Cost if Landfilled ($) | * Savings from Diversion | 0
Concrete | 32482.8532 | 333000 | -300517.1468 | 370000 | -670517.1468 | 670517.1468
Asphalt | 2737.7778 | 924 | 1813.7778 | 4620 | -2806.2222 | 673323.369
Metals - All Types | 59600 | 72420 | -12820 | 14459.38 | -27279.38 | 700602.749
Electric Cable | 2274 | 6064 | -3790 | 75.8 | -3865.8 | 704468.549
Asphalt | 0 | 0% | 0
C&D (Landfill) | 960000 | 99% | 480
Concrete (Recycled) | 0 | 0% | 0
Metals - All Types (Recycled) | 4000 | 1% | 2
| 964000 | 1%