## StaffingTbl
Proprietary; Procurement Sensitive The information in this document is proprietary. It may not be used, reproduced, disclosed, or exported without written approval.
W9124D23R0007 | USAREC ITSS | [15 empty] | Write up on how we know it takes the level of effort and which past program/analogous program or model (e.g. erlang model for call centers) supports this? Make sure you read the PWS and review the deliverables needed. | Most relevant PP Reference, if more than one or need to add others see PP Rationale Tab - add there then use dropdown | Enter Assumptions | Enter any Risks and the Risk Mitigation Plan
FTE = | 1872 | [8 empty] | Phase-In | Base Period | Option Period 1 | Option Period 2 | Option Period 3 | Option Period 4
Instructions: Please fill in the yellow highlighted cells and add rows if needed. Especially to break out help desk and other staff by location. If the staffing changes in the Option Periods, enter the hours, otherwise the LOE is steady state from the Base Period. You can sort and filter this table as needed. | [9 empty] | 2023-01-01 | 2023-02-01 | 2024-02-01 | 2025-02-01 | 2026-02-01 | 2027-02-01
[10 empty] | 2023-01-31 | 2024-01-31 | 2025-01-31 | 2026-01-31 | 2027-01-31 | 2028-01-31
[6 empty] | What org within your Org Chart is this person part of? |  |  | TOTAL FTEs = | 1 | 45.5422 | 45.5 | 45.5 | 45.5 | 45.5
CLIN | WBS | PWS | LaborCategory | Level | Role | Organization | Company | Location | COMMENTS | PhaseIn | BasePeriod | OP1 | OP2 | OP3 | OP4 | TOTAL | Rationale | RelevantPP | Assumptions | Risks | Personnel From | Key Role = 1 | ID
0002 |  | 1.3.1 Functional Support (5.1. Functional Support) | Software Developer, Applications |  | Software Developer | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 6
0002 |  | 1.3.1 Functional Support (5.1. Functional Support) | Database Architect |  | Data Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 14
0002 |  | 1.3.3 Business Process Modeling (5.3. Business Process Modeling) | Database Architect |  | Data Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 64
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 78
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Computer Systems Engineer/Architect |  | Solutions Architect | [5 empty] | 655.2 | 655.2 | 655.2 | 655.2 | 655.2 | 3276 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 79
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Computer Systems Engineer/Architect |  | Systems Engineer | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 80
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Software Developer, Applications |  | Software Developer | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 81
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Computer Network Support Specialist |  | Network Engineer | [5 empty] | 468 | 468 | 468 | 468 | 468 | 2340 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 82
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Web Developer |  | UI/UX Designer / Computer Graphics Specialist | [5 empty] | 1310.4 | 1310.4 | 1310.4 | 1310.4 | 1310.4 | 6552 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 85
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Technical Writer |  | Technical Editor/Writer | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 86
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Software Quality Assurance Engineer and Tester |  | QA/Testing Specialists | [5 empty] | 748.8 | 748.8 | 748.8 | 748.8 | 748.8 | 3744 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 87
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Database Architect |  | Data Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 89
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Training and Development Specialist |  | Training Specialist | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 95
0002 |  | 1.3.4 Software Engineering (5.4. Software Engineering) | Management Analyst |  | Asset / O&M Manager (Configuration Mgmt) | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 99
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 103
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Computer Systems Engineer/Architect |  | Solutions Architect | [5 empty] | 280.8 | 280.8 | 280.8 | 280.8 | 280.8 | 1404 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 104
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Computer Systems Engineer/Architect |  | Systems Engineer | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 105
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Software Developer, Applications |  | Software Developer | [5 empty] | 468 | 468 | 468 | 468 | 468 | 2340 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 106
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Computer Network Support Specialist |  | Network Engineer | [5 empty] | 234 | 234 | 234 | 234 | 234 | 1170 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 107
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Web Developer |  | Web Development Specialist | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 109
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Technical Writer |  | Technical Editor/Writer | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 111
0002 |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | Database Architect |  | Data Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 114
0002 |  | 1.3.6 Data Engineering (5.6. Data Engineering) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 128
0002 |  | 1.3.6 Data Engineering (5.6. Data Engineering) | Computer Systems Engineer/Architect |  | Solutions Architect | [5 empty] | 280.8 | 280.8 | 280.8 | 280.8 | 280.8 | 1404 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 129
0002 |  | 1.3.6 Data Engineering (5.6. Data Engineering) | Database Architect |  | Data Architect | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 139
0002 |  | 1.3.6 Data Engineering (5.6. Data Engineering) | Database Administrator |  | Database Administrator | [5 empty] | 468 | 468 | 468 | 468 | 468 | 2340 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 141
0002 |  | 1.3.6 Data Engineering (5.6. Data Engineering) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 143
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 153
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Computer Systems Engineer/Architect |  | Solutions Architect | [5 empty] | 468 | 468 | 468 | 468 | 468 | 2340 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 154
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Software Developer, Applications |  | Software Developer | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 156
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Software Quality Assurance Engineer and Tester |  | QA/Testing Specialists | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 162
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Database Architect |  | Data Architect | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 164
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Database Administrator |  | Database Administrator | [5 empty] | 1404 | 1404 | 1404 | 1404 | 1404 | 7020 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 166
0002 |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 168
0002 |  | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | Information Technology Project Manager |  | Program Manager/Corporate Liaison | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel Available within Company | Yes | 176
0001 |  | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | Information Technology Project Manager |  | Transition Manager |  |  |  |  | 156 | 79 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Personnel Available within Company | Yes | 177
0002 |  | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | Information Technology Project Manager |  | Project Manager | [5 empty] | 1123.2 | 1123.2 | 1123.2 | 1123.2 | 1123.2 | 5616 |  |  |  |  | Personnel Available within Company |  | 178
0002 |  | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | Senior Software Quality Assurance Engineer and Tester |  | Quality Assurance Manager | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 188
0002 |  | 1.3.9 Project Control (5.9 Project Control) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 203
0002 |  | 1.3.9 Project Control (5.9 Project Control) |  |  | Scheduler | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 219
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 228
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Computer Systems Engineer/Architect |  | Solutions Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 229
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Computer Systems Engineer/Architect |  | Systems Engineer | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 230
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Software Developer, Applications |  | Software Developer | [5 empty] | 468 | 468 | 468 | 468 | 468 | 2340 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 231
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Web Developer |  | UI/UX Designer / Computer Graphics Specialist | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 235
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Technical Writer |  | Technical Editor/Writer | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 236
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Software Quality Assurance Engineer and Tester |  | QA/Testing Specialists | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 237
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Database Architect |  | Data Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 239
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Training and Development Specialist |  | Training Specialist | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 245
0002 |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | Management Analyst |  | Asset / O&M Manager (Configuration Mgmt) | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 249
0002 |  | 1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 253
0002 |  | 1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 3744 | 3744 | 3744 | 3744 | 3744 | 18720 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 268
0002 |  | 1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) | Training and Development Specialist |  | Training Specialist | [5 empty] | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 7488 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 270
0002 |  | 1.3.12 Process Improvement (5.12. Process Improvement) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 278
0002 |  | 1.3.12 Process Improvement (5.12. Process Improvement) | Senior Software Quality Assurance Engineer and Tester |  | Quality Assurance Manager | [5 empty] | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 7488 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 288
0002 |  | 1.3.12 Process Improvement (5.12. Process Improvement) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 293
0002 |  | 1.3.12 Process Improvement (5.12. Process Improvement) | Business Intelligence |  | SME - Process Improvement, Business Intelligence | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 296
0002 |  | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 303
0002 |  | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 318
0003 |  | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | Computer User Support Specialist |  | Service Desk Technician | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 322
0002 |  | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | Computer Network Support Specialist |  | Service Desk Manager | [5 empty] | 93.6 | 93.6 | 93.6 | 93.6 | 93.6 | 468 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 323
0002 |  | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | Management Analyst |  | Asset / O&M Manager (Configuration Mgmt) | [5 empty] | 1310.4 | 1310.4 | 1310.4 | 1310.4 | 1310.4 | 6552 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 324
0002 |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 328
0002 |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | Computer Network Support Specialist |  | Network Engineer | [5 empty] | 234 | 234 | 234 | 234 | 234 | 1170 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 332
0002 |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | Telecom Engineering Specialist |  | Telecom Control Officer | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 340
0002 |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 343
0003 |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | Computer User Support Specialist |  | Service Desk Technician | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 347
0002 |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | Computer Network Support Specialist |  | Service Desk Manager | [5 empty] | 93.6 | 93.6 | 93.6 | 93.6 | 93.6 | 468 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 348
0002 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 353
0002 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Software Developer, Applications |  | Software Developer | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 356
0002 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Software Quality Assurance Engineer and Tester |  | QA/Testing Specialists | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 362
0002 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Senior Software Quality Assurance Engineer and Tester |  | Quality Assurance Manager | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 363
0002 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 368
0003 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Computer User Support Specialist |  | Service Desk Technician | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 372
0002 |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | Management Analyst |  | Asset / O&M Manager (Configuration Mgmt) | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 374
0002 |  | 1.3.16 Business Intelligence (5.16. Business Intelligence Experience) | Information Technology Project Manager |  | Project Manager | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel Available within Company |  | 378
0002 |  | 1.3.16 Business Intelligence (5.16. Business Intelligence Experience) | Business Intelligence Analyst |  | Business Analyst | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 393
0002 |  | 1.3.16 Business Intelligence (5.16. Business Intelligence Experience) | Business Intelligence |  | SME - Process Improvement, Business Intelligence | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 396
0002 |  | 1.3.17 General System Support (5.17 General System Support) | Database Architect |  | Data Architect | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 414
0003 |  | 1.3.18 Helpdesk Support (5.20. Incident Management (Split amongst locations)) | Computer User Support Specialist |  | Service Desk Technician | [5 empty] | 10296 | 10296 | 10296 | 10296 | 10296 | 51480 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 447
0002 |  | 1.3.18 Helpdesk Support (5.20. Incident Management (Split amongst locations)) | Computer Network Support Specialist |  | Service Desk Manager | [5 empty] | 1684.8 | 1684.8 | 1684.8 | 1684.8 | 1684.8 | 8424 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 448
0002 |  | 1.3.19 IT Administrative Support Services (5.22. Support the administration of the IT workforce readiness & 5.23. Administrative Support) | Technical Writer |  | Technical Editor/Writer | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 461
0002 |  | 5.18. Computer Graphics (CG) | Web Developer |  | UI/UX Designer / Computer Graphics Specialist | [5 empty] | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 1872 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 485
0002 |  | 5.19. Technical Writers | Technical Writer |  | Technical Editor/Writer | [5 empty] | 1123.2 | 1123.2 | 1123.2 | 1123.2 | 1123.2 | 5616 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 511
0002 |  | 5.21. Information Management Services | Technical Writer |  | Technical Editor/Writer | [5 empty] | 187.2 | 187.2 | 187.2 | 187.2 | 187.2 | 936 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 536
0002 |  | 5.24 Network Operations | Computer Network Support Specialist |  | Network Engineer | [5 empty] | 936 | 936 | 936 | 936 | 936 | 4680 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 557
0002 |  | 5.24 Network Operations | Computer Network Support Specialist |  | Network Administrator | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 558
0003 |  | 5.24 Network Operations |  |  | Clerk / Administrative Assistant | [5 empty] | 1872 | 1872 | 1872 | 1872 | 1872 | 9360 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 575
0002 |  | 5.25. Cyber Security | Information Security Analyst |  | Cyber Security Specialist | [5 empty] | 3744 | 3744 | 3744 | 3744 | 3744 | 18720 |  |  |  |  | Personnel to be Obtained from Incumbent |  | 592
[11 empty] | 85255 | 85176 | 85176 | 85176 | 85176
Proprietary; Procurement Sensitive The information in this document is proprietary. It may not be used, reproduced, disclosed, or exported without written approval.

## WBS
Please map the PWS to the WBS
Count | Level | WBS # | WBS Description | PWS
1 | Level 1 | 1.0 | Information Systems (IS)/Defense Business Systems (DBS) (Investment) |  | 1.3.1 Functional Support (5.1. Functional Support) | 1.0 Information Systems (IS)/Defense Business Systems (DBS) (Investment)
2 | Level 2 | 1.1 | IS/DBS Development/Customization/Configuration |  | 1.3.2 Requirements Engineering (5.2. Requirements Engineering) | 1.1 IS/DBS Development/Customization/Configuration
3 | Level 3 | 1.1.1 | Custom Application 1...n (Specify) | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | 1.3.3 Business Process Modeling (5.3. Business Process Modeling) | 1.1.1 Custom Application 1...n (Specify)
4 | Level 4 | 1.1.1.1 | Subsystem Hardware (Specify) |  | 1.3.4 Software Engineering (5.4. Software Engineering) | 1.1.1.1 Subsystem Hardware (Specify)
5 | Level 4 | 1.1.1.2 | Subsystem Software CSCI 1...n (Specify) |  | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | 1.1.1.2 Subsystem Software CSCI 1...n (Specify)
6 | Level 4 | 1.1.1.3 | Subsystem Software Level Integration, Assembly, Test, and Checkout |  | 1.3.6 Data Engineering (5.6. Data Engineering) | 1.1.1.3 Subsystem Software Level Integration, Assembly, Test, and Checkout
7 | Level 3 | 1.1.2 | Enterprise Service Element 1...n (Specify) |  | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | 1.1.2 Enterprise Service Element 1...n (Specify)
8 | Level 4 | 1.1.2.1 | Enterprise Service Element Hardware (Specify) |  | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | 1.1.2.1 Enterprise Service Element Hardware (Specify)
9 | Level 4 | 1.1.2.2 | Enterprise Service Element Software CSCI 1...n (Specify) |  | 1.3.9 Project Control (5.9 Project Control) | 1.1.2.2 Enterprise Service Element Software CSCI 1...n (Specify)
10 | Level 4 | 1.1.2.3 | Enterprise Service Element Integration, Assembly, Test, and Checkout |  | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | 1.1.2.3 Enterprise Service Element Integration, Assembly, Test, and Checkout
11 | Level 3 | 1.1.3 | Enterprise/Management Information System 1...n (Specify) | 5.21. Information Management Services | 1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) | 1.1.3 Enterprise/Management Information System 1...n (Specify)
12 | Level 4 | 1.1.3.1 | Business Area Hardware (Specify) |  | 1.3.12 Process Improvement (5.12. Process Improvement) | 1.1.3.1 Business Area Hardware (Specify)
13 | Level 4 | 1.1.3.2 | Business Area Software CSCI 1...n (Specify) |  | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | 1.1.3.2 Business Area Software CSCI 1...n (Specify)
14 | Level 4 | 1.1.3.3 | Business Area Integration, Assembly, Test, and Checkout |  | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | 1.1.3.3 Business Area Integration, Assembly, Test, and Checkout
15 | Level 3 | 1.1.4 | External System Interface Development 1...n (Specify) |  | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | 1.1.4 External System Interface Development 1...n (Specify)
16 | Level 4 | 1.1.4.1 | External System Interface Hardware (Specify) |  | 1.3.16 Business Intelligence (5.16. Business Intelligence Experience) | 1.1.4.1 External System Interface Hardware (Specify)
17 | Level 4 | 1.1.4.2 | External System Interface Software CSCI 1...n (Specify) |  | 1.3.17 General System Support (5.17 General System Support) | 1.1.4.2 External System Interface Software CSCI 1...n (Specify)
18 | Level 4 | 1.1.4.3 | External System Interface Integration, Assembly, Test, and Checkout |  | 1.3.18 Helpdesk Support (5.20. Incident Management (Split amongst locations)) | 1.1.4.3 External System Interface Integration, Assembly, Test, and Checkout
19 | Level 3 | 1.1.5 | System Level Infrastructure (Specify) |  | 1.3.19 IT Administrative Support Services (5.22. Support the administration of the IT workforce readiness & 5.23. Administrative Support) | 1.1.5 System Level Infrastructure (Specify)
20 | Level 4 | 1.1.5.1 | System Level Hardware (Specify) |  | 5.18. Computer Graphics (CG) | 1.1.5.1 System Level Hardware (Specify)
21 | Level 4 | 1.1.5.2 | Service Infrastructure 1...n (Specify) |  | 5.19. Technical Writers | 1.1.5.2 Service Infrastructure 1...n (Specify)
22 | Level 2 | 1.2 | System Level Integration |  | 5.21. Information Management Services | 1.2 System Level Integration
23 | Level 2 | 1.3 | Systems Engineering |  | 5.24 Network Operations | 1.3 Systems Engineering
24 | Level 3 | 1.3.1 | Software Systems Engineering | 1.3.2 Requirements Engineering (5.2. Requirements Engineering) 1.3.4 Software Engineering (5.4. Software Engineering) 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | 5.25. Cyber Security | 1.3.1 Software Systems Engineering
25 | Level 3 | 1.3.2 | Integrated Logistics Support (ILS) Systems Engineering | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) |  | 1.3.2 Integrated Logistics Support (ILS) Systems Engineering
26 | Level 3 | 1.3.3 | Cybersecurity Systems Engineering | 5.25 Cyber Security |  | 1.3.3 Cybersecurity Systems Engineering
27 | Level 3 | 1.3.4 | Core Systems Engineering |  |  | 1.3.4 Core Systems Engineering
28 | Level 3 | 1.3.5 | Other Systems Engineering 1...n (Specify) | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) |  | 1.3.5 Other Systems Engineering 1...n (Specify)
29 | Level 2 | 1.4 | Program Management | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) 1.3.9 Project Control (5.9 Project Control) |  | 1.4 Program Management
30 | Level 3 | 1.4.1 | Software Program Management |  |  | 1.4.1 Software Program Management
31 | Level 3 | 1.4.2 | Integrated Logistics Support (ILS) Program Management |  |  | 1.4.2 Integrated Logistics Support (ILS) Program Management
32 | Level 3 | 1.4.3 | Cybersecurity Program Management |  |  | 1.4.3 Cybersecurity Program Management
33 | Level 3 | 1.4.4 | Core Program Management |  |  | 1.4.4 Core Program Management
34 | Level 3 | 1.4.5 | Other Program Management 1...n (Specify) |  |  | 1.4.5 Other Program Management 1...n (Specify)
35 | Level 2 | 1.5 | Change Management | 1.3.12 Process Improvement (5.12. Process Improvement) |  | 1.5 Change Management
36 | Level 2 | 1.6 | Data Management | 1.3.6 Data Engineering (5.6. Data Engineering); 1.3.7 Database Management and Administration (5.7. Database Management and Administration) |  | 1.6 Data Management
37 | Level 2 | 1.7 | System Test and Evaluation | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) |  | 1.7 System Test and Evaluation
38 | Level 3 | 1.7.1 | Developmental Test and Evaluation |  |  | 1.7.1 Developmental Test and Evaluation
39 | Level 4 | 1.7.1.1 | Cybersecurity Test and Evaluation |  |  | 1.7.1.1 Cybersecurity Test and Evaluation
40 | Level 4 | 1.7.1.2 | Other DT&E Tests 1…n (Specify) |  |  | 1.7.1.2 Other DT&E Tests 1…n (Specify)
41 | Level 3 | 1.7.2 | Operational Test and Evaluation |  |  | 1.7.2 Operational Test and Evaluation
42 | Level 4 | 1.7.2.1 | Cybersecurity Test and Evaluation |  |  | 1.7.2.1 Cybersecurity Test and Evaluation
43 | Level 4 | 1.7.2.2 | Other OT&E Tests 1…n (Specify) |  |  | 1.7.2.2 Other OT&E Tests 1…n (Specify)
44 | Level 3 | 1.7.3 | Mock-ups/System Integration Labs (SILs |  |  | 1.7.3 Mock-ups/System Integration Labs (SILs
45 | Level 3 | 1.7.4 | Test and Evaluation Management/Support |  |  | 1.7.4 Test and Evaluation Management/Support
46 | Level 3 | 1.7.5 | Test Facilities |  |  | 1.7.5 Test Facilities
47 | Level 2 | 1.8 | Training | 1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) |  | 1.8 Training
48 | Level 3 | 1.8.1 | Equipment |  |  | 1.8.1 Equipment
49 | Level 3 | 1.8.2 | Services |  |  | 1.8.2 Services
50 | Level 3 | 1.8.3 | Facilities |  |  | 1.8.3 Facilities
51 | Level 3 | 1.8.4 | Training Software 1...n (Specify) |  |  | 1.8.4 Training Software 1...n (Specify)
52 | Level 2 | 1.9 | Data |  |  | 1.9 Data
53 | Level 3 | 1.9.1 | Data Deliverables 1...n (Specify) |  |  | 1.9.1 Data Deliverables 1...n (Specify)
54 | Level 3 | 1.9.2 | Data Repository |  |  | 1.9.2 Data Repository
55 | Level 3 | 1.9.3 | Data Rights 1...n (Specify) |  |  | 1.9.3 Data Rights 1...n (Specify)
56 | Level 2 | 1.10 | Peculiar Support Equipment |  |  | 1.10 Peculiar Support Equipment
57 | Level 3 | 1.10.1 | Test and Measurement Equipment |  |  | 1.10.1 Test and Measurement Equipment
58 | Level 3 | 1.10.2 | Support and Handling Equipment |  |  | 1.10.2 Support and Handling Equipment
59 | Level 2 | 1.11 | Common Support Equipment |  |  | 1.11 Common Support Equipment
60 | Level 3 | 1.11.1 | Test and Measurement Equipment |  |  | 1.11.1 Test and Measurement Equipment
61 | Level 3 | 1.11.2 | Support and Handling Equipment |  |  | 1.11.2 Support and Handling Equipment
62 | Level 2 | 1.12 | Operational Infrastructure/Site Activation by Site 1...n (Specify) |  |  | 1.12 Operational Infrastructure/Site Activation by Site 1...n (Specify)
63 | Level 3 | 1.12.1 | Initial Hardware Procurement |  |  | 1.12.1 Initial Hardware Procurement
64 | Level 4 | 1.12.1.1 | End User Equipment |  |  | 1.12.1.1 End User Equipment
65 | Level 4 | 1.12.1.2 | Cybersecurity Equipment |  |  | 1.12.1.2 Cybersecurity Equipment
66 | Level 4 | 1.12.1.3 | IT Infrastructure and Enterprise Software Equipment |  |  | 1.12.1.3 IT Infrastructure and Enterprise Software Equipment
67 | Level 4 | 1.12.1.4 | Other 1...n (Specify) |  |  | 1.12.1.4 Other 1...n (Specify)
68 | Level 3 | 1.12.2 | Initial Software License Procurement |  |  | 1.12.2 Initial Software License Procurement
69 | Level 4 | 1.12.2.1 | End User Software License |  |  | 1.12.2.1 End User Software License
70 | Level 4 | 1.12.2.2 | Cybersecurity Software Licenses/Services |  |  | 1.12.2.2 Cybersecurity Software Licenses/Services
71 | Level 4 | 1.12.2.3 | IT Infrastructure and Equipment |  |  | 1.12.2.3 IT Infrastructure and Equipment
72 | Level 4 | 1.12.2.4 | Other 1...n (Specify) |  |  | 1.12.2.4 Other 1...n (Specify)
73 | Level 3 | 1.12.3 | Initial Software Release (Pre-IOC) Modification/Enhancement |  |  | 1.12.3 Initial Software Release (Pre-IOC) Modification/Enhancement
74 | Level 4 | 1.12.3.1 | Routine Fixes/Deficiency Correction |  |  | 1.12.3.1 Routine Fixes/Deficiency Correction
75 | Level 4 | 1.12.3.2 | Deployment Independent Verification and Validation |  |  | 1.12.3.2 Deployment Independent Verification and Validation
76 | Level 4 | 1.12.3.3 | Installation/Test |  |  | 1.12.3.3 Installation/Test
77 | Level 3 | 1.12.4 | Site Activation |  |  | 1.12.4 Site Activation
78 | Level 4 | 1.12.4.1 | Data Migration |  |  | 1.12.4.1 Data Migration
79 | Level 4 | 1.12.4.2 | User Training |  |  | 1.12.4.2 User Training
80 | Level 4 | 1.12.4.3 | User Documentation |  |  | 1.12.4.3 User Documentation
81 | Level 4 | 1.12.4.4 | Management/Engineering Support |  |  | 1.12.4.4 Management/Engineering Support
82 | Level 4 | 1.12.4.5 | Site Installation, Test, and Checkout |  |  | 1.12.4.5 Site Installation, Test, and Checkout
83 | Level 3 | 1.12.5 | Interim Operations and Support (Pre-IOC) |  |  | 1.12.5 Interim Operations and Support (Pre-IOC)
84 | Level 4 | 1.12.5.1 | Help Desk | 1.3.18 Helpdesk Support (5.20. Incident Management (Split amongst locations)) |  | 1.12.5.1 Help Desk
85 | Level 4 | 1.12.5.2 | System Database Administrator |  |  | 1.12.5.2 System Database Administrator
86 | Level 4 | 1.12.5.3 | Installation, Test, and Checkout |  |  | 1.12.5.3 Installation, Test, and Checkout
87 | Level 4 | 1.12.5.4 | IT Equipment Maintenance |  |  | 1.12.5.4 IT Equipment Maintenance
88 | Level 2 | 1.13 | Industrial Facilities |  |  | 1.13 Industrial Facilities
89 | Level 3 | 1.13.1 | Construction/Conversion/Expansion |  |  | 1.13.1 Construction/Conversion/Expansion
90 | Level 3 | 1.13.2 | Equipment Acquisition or Modernization |  |  | 1.13.2 Equipment Acquisition or Modernization
91 | Level 3 | 1.13.3 | Maintenance (Industrial Facilities) |  |  | 1.13.3 Maintenance (Industrial Facilities)
92 | Level 2 | 1.14 | Initial Spares and Repair Parts |  |  | 1.14 Initial Spares and Repair Parts

## PP Rationale
Short Name | Name | Size (Annual, $M) | Summary
OTJ | OT JAG | 6M | Web Development and Maintenace; includes Help Desk and considerable KM; > 10,000 users
NOMB | NOMB | 5M | Cloud Architecture; Cloud Migration; NW Management; Agile Dev
CENA | Marine Corp CENA | 6M | Analytics Program; Estimating Capabilities; Tools
TRLS | DTRA TRLS | 30M | Logistics and travel management - Help Desk, have 2 FTEs, 1 Cyber and 1 SW Usage/Application Usage
TFMMS | NAVY TFMMS | 1M | SW Dev. Maintain GOTS. Great CPARS. Agile. Cross Domain Networks.
NSD | DHS NSD | 8M | Cybersecurity support to DHS. No CPARS.

## Notes and Ground Rules
Proprietary; Procurement Sensitive
The information in this document is proprietary.
It may not be used, reproduced, disclosed, or exported without written approval.
Ground Rules
| 5.1 | May not be descrete labor here | Assumption: The G6 CIO/government has an overarching Cybersecurity program being handled outside this program by another vendor or the Government. We support Cyber within this USAREC Domain to the extent that this contract interfaces with the applicable networks, apps, etc.
| 5.2 | Revisit
| 5.3 | Software Engineering completion
| 5.4 | Calls back to the service desk (those activities are in a diferent PWS)
| 5.7 | Monitoring apps on the network; not the front line cyber support
Proprietary; Procurement Sensitive
The information in this document is proprietary.
It may not be used, reproduced, disclosed, or exported without written approval.

## Data Lists
PWS | WBS | LaborCategories | PWSDescription | PWSPerformanceStandard | Location
1.3.1 Functional Support (5.1. Functional Support) | 1.0 Information Systems (IS)/Defense Business Systems (DBS) (Investment) | Business Intelligence Analyst, Junior | 5. Specific Tasks: Information Technology Support Services |  | Government Site
1.3.2 Requirements Engineering (5.2. Requirements Engineering) | 1.1 IS/DBS Development/Customization/Configuration | Business Intelligence Analyst, Journeyman | 5.1. Functional Support. The contractor shall provide support services to the USAREC IT Projects, Programs, and Planning Division (P3MD). The contractor will support specific functional areas such as: requirements systems maintenance, sustainment, minor development, information management, business process modeling, enterprise architecture, data engineering, database management and administration, documentation, training, deploying software maintenance, integration engineering, process improvement, project management, and application software post-deployment support. 5.1.1. The contractor shall provide support services for IT sustainment. 5.1.2. The contractor shall support requirements development and sustainment for new and revised government applications and COTS application software supporting functional requirements. 5.1.3. The contractor shall deploy and sustain new and revised Government applications and COTS application software supporting functional requirements. 5.1.4. The contractor shall provide support services to the Government in the management and technical integration of externally developed products, modules, and/or applications into the existing architecture. | The contractor shall provide support services to the USAREC IT Projects, Programs, and Planning Division (P3MD). The contractor shall meet a minimum of 95% of all assigned project and task associated timelines Contractor compliance will be monitored for CPAR reporting | Contractor Site
1.3.3 Business Process Modeling (5.3. Business Process Modeling) | 1.1.1 Custom Application 1...n (Specify) | Business Intelligence Analyst, Senior | 5.2. Requirements Engineering. The Government will provide needed modification requirements via government-issued actions such as scope documents, requirement documents, change requests, problem reports, and troubleshooting and/or other maintenance tasks related to the sustainment of production systems. The contractor shall: 5.2.1. Determine, analyze, and validate detailed requirements specifications. 5.2.2. Perform requirements change management. 5.2.3. Document detailed requirements and design specifications by Government policies, processes, and procedures: 5.2.3.1. Maintain version control of architecture products using approved version control processes. 5.2.3.2. Maintain compliance with Business Enterprise Architecture (BEA) 5.0, and future versions. 5.2.3.3. Maintain architecture accuracy compliant with the Department of Defense Architecture Framework (DODAF) 2.0 and future versions. 5.2.3.4. Maintain the All Viewpoint that describes the overarching aspects of architecture context that relate to all viewpoints. 5.2.3.5. Maintain the Capability Viewpoint that articulates the capability requirements, the delivery timing, and the deployed capability. 5.2.3.6. Maintain the Data and Information Viewpoint that articulates the data relationships and alignment structures in the architecture content for the capability and operational requirements, system engineering processes, and systems and services. 5.2.3.7. Maintain the Operational Viewpoint that includes the operational scenarios, activities, and requirements that support capabilities. 5.2.3.8. Maintain the Services Viewpoint that includes the design for solutions articulating the Performers, Activities, Services, and their Exchanges, providing for or supporting operational and capability functions. 5.2.3.9. Maintain the Standards Viewpoint that articulates the applicable operational, business, technical, and industry policies, standards, guidance, constraints, and forecasts that apply to capability and operational requirements, system engineering processes, and systems. 5.2.3.10. Maintain the Systems Viewpoint that describes the design for solutions articulating the systems, their composition, interconnectivity, and context providing for or supporting operational and capability functions. Must provide updates within 24 hours to Government as changes occur. | Conduct or support formal Requirement Review for each software engineering project; all projects must be traceable between requirements The contractor shall meet 100% of Business Enterprise Architecture 5.0 requirements and a minimum of 95% of all assigned Business Modeling project tasks and milestones Contractor compliance will be monitored for CPAR reporting | USAREC Fort Knox, KY
1.3.4 Software Engineering (5.4. Software Engineering) | 1.1.1.1 Subsystem Hardware (Specify) | Business Intelligence Analyst, SME | 5.3. Business Process Modeling. The contractor shall: 5.3.1. Develop, document, and integrate Business Process Models (BPM). BPMs shall be constructed with IAW Government guidelines and instructions. BPM work products and activities include: 5.3.1.1. Maintain version control of architecture products using approved version control processes. 5.3.1.2. Maintain compliance with Business Enterprise Architecture (BEA) 5.0 or the current version. 5.3.1.3. Compliance with DOD and DA guidelines for business process modeling notation (BPMN). 5.3.2. Software requirements work products and activities include: 5.3.2.1. Development and maintenance of use cases. 5.3.2.2. Preparation and maintenance of user stories. 5.3.2.3. Traceability between requirements. 5.3.2.4. Screen prototypes. 5.3.2.5. Identifying non-functional requirements for system service level and service level agreements, screen design, usability, and information architecture. 5.3.2.6. Maintain traceability from change request to requirement to software unit and version throughout the requirement. Must provide to the Government within 72 hours of completion. 5.3.3. Conduct formal Requirement Reviews for projects (an average of 150 projects over a five-year period). The Government functional representative(s) and the appointed representatives will be the approval authorities. | Develop, document, and integrate Business Process Models (BPM). BPMs shall be constructed with IAW Government guidelines and instructions The contractor shall meet a minimum of 95% of all software engineering project tasks and milestones Contractor compliance will be monitored for CPAR reporting | AMU, Fort Benning, GA
1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | 1.1.1.2 Subsystem Software CSCI 1...n (Specify) | Computer and Information Research Scientist, Junior | 5.4. Software Engineering. Software development activities are limited to minor development incidental to systems maintenance and sustainment, which may include minor code construction, populating databases, integrating services, and other data files with data values; and other activities needed to implement the requirements and design. All activities must be presented to Government in the timeline set when acquiring the project. The Government, at its discretion and with approval of the Contracting Officer, may ask the contractor to follow an alternate development process or may waive some documentation requirements, particularly with minor change requests. The contractor shall: 5.4.1. Conduct software-engineering activities using applicable DoD and DA policies and standards, and industry best practices when applicable. 5.4.2. Perform minor software configuration, using requirements provided by functional and technical leads, including maintenance and sustainment of the architectural design and the detailed design. 5.4.3. Provide and store specific documentation and work products as defined by USAREC G6 software engineering methodologies. 5.4.4. Ensure developed products comply with appropriate and current Defense Information Security Agency DISA Security Technical Implementation Guides, including the Application and Security Development. 5.4.5. The contractor shall perform architectural design and the detailed design of each Configuration Item, as well as definition and recording of design decisions and descriptions. Documents shall be submitted to the Government within 24 hours of completion. Work products shall include designs and documentation such as: 5.4.5.1. Architectural designs, including identification of the software units comprising the CI, their interfaces, the integration between them, and the traceability between the software units and the Cl requirements. 5.4.5.2. Architectural design descriptions (e.g., interface software unit descriptions, interface descriptions, design descriptions, and database design descriptions). 5.4.5.3. Detailed design and description of each of the software units comprising a CI, (e.g., data manipulation, database access, and external and internal interfaces). 5.4.5.4. The contractor shall conduct formal design reviews by USAREC G6 methodologies. 5.4.6. Develop documentation for the software corresponding to each CI and the individual software units comprising the CI within 24 hours of meeting. All documents shall meet established guidelines within each project. All discretionary decisions will be made by the Government. The contractor shall draft documentation of such decisions. These documents include: 5.4.6.1. Project management plan. 5.4.6.2. Requirements documents. 5.4.6.3. Systems interface agreements 5.4.6.4. Memorandums of agreement. 5.4.6.5. Software installation work instructions. 5.4.6.6. Service Level Agreements. 5.4.6.7. Use case documents. 5.4.6.8. User stories. 5.4.6.9. Systems (and data) Transition Plan. 5.4.6.10. Software Version Description. 5.4.6.11. Data Flow Diagrams. 5.4.7. Integrate software corresponding to two or more software units; test the resulting software to ensure that it works as intended. A report shall be given to the Government detailing test results. 5.4.8. Provide support services for the creation and maintenance of documentation for developer environments including: 5.4.8.1. Maintenance of standards and procedures for the developer environment 5.4.8.2. COTS material may be used where applicable, including Government acquisition of required updates and upgrades, as well as the material available for public use. 5.4.8.3. Documentation shall be in electronic format and indexed, providing rapid access to the information. 5.4.9. Create and maintain user and operations documentation including: 5.4.9.1. The development and maintenance of documentation for the users and operators of the system(s), updated and modified, as required, for the life of the system(s) or module user manuals, containing information needed by hands-on users of the software. 5.4.9.2. Quick reference materials, with system tips and reminders. 5.4.9.3. COTS material may be used where applicable, including Government acquisition of required updates and upgrades, as well as the material available for public use. 5.4.9.4. Operations documentation developed for the system(s) that may be updated and modified as required for the life of the system(s). Operations documentation work products may include computer operation manuals, which contain information needed to operate the computer software. 5.4.9.5. Documentation shall be in electronic format and indexed, providing rapid access to the information. 5.4.10. Provide all configuration items to the Configuration Management team within 72 hours of receipt of CI from the service provider. 5.4.11. Provide support services for software deployments to include, planning, preparation, and the fielding of software change packages, software components, and databases. The contractor shall plan and document software integration, installation, support activities, and training, including user, test-er, system administrator, and Customer Service Center personnel training. 5.4.12. Support or conduct a User Decision Meeting for each project before the deployment phase by established methodologies. The Government functional representative(s) or designated representative will act as the approval authority for the UDM. 5.4.13. Executable software shall specify all batch files, command files, services, media files, image files, script files, database files, data files, and/or other software type files needed to be installed or accessed to ensure successful operation of the software on the target configuration. 5.4.14. Prepare version descriptions that identify and describe the exact version of software prepared for each site. Work products shall include: 5.4.14.1. Software installation and integration plans. 5.4.14.2. Executable software and supporting documentation. 5.4.14.3. Software Version Descriptions. 5.4.15. Provide support services for other software deployment activities to include data migration, system deployment, and architecture component deployment. Work products include: 5.4.15.1. Fielding integration procedures, to include all aspects of data migration. 5.4.15.2. Automated installation procedures in support of the deployment of the systems software modules. 5.4.15.3. Architecture component deployment and fielding activities, such as site surveys (in coordination with the Communications, Electronics, and Operations MAM), and problem identification, isolation, and correction. 5.4.15.4. Training materials for users, Customer Support Center personnel, and supporting technical personnel before and during the deployment period. 5.4.16. Perform software lifecycle maintenance, as required, for any identified system or module. The contractor shall perform the same tasks described and update any plans and procedures that are impacted because of maintenance activities. A requirement for non-periodic software maintenance support shall be documented and communicated using a Request for Change. 5.4.17. Provide support services for operations by performing the following activities including: 5.4.17.1. Monitoring interfaces to ensure data is correctly sent and received with other modules and/or systems. 5.4.17.2. Monitoring production batch activities to ensure proper execution. 5.4.17.3. Resolving expeditiously any errors in production cycles to complete production activity. 5.4.17.4. Providing Level III and IV support to the customer to resolve production issues and/or guide customers and guidance training to support personnel. (Level III support refers to providing help with problems that are not resolved by the support and Level IV refers to requiring the assistance of a highly technical and knowledgeable software engineer or equivalent). 5.4.17.5. Within 30 minutes, assess identified reported system issues, failures and immediately initiate notifications and alerts through established procedures provided by the Government. 5.4.17.6. Identify and resolve problems in production systems. | Conduct or support formal Requirement Review for each software engineering project; all projects must be traceable between requirements The contractor shall meet a minimum of 95% of all software engineering project tasks and milestones Contractor compliance will be monitored for CPAR reporting | SORB, Fort Bragg NC
1.3.6 Data Engineering (5.6. Data Engineering) | 1.1.1.3 Subsystem Software Level Integration, Assembly, Test, and Checkout | Computer and Information Research Scientist, Journeyman | 5.5. Applications and Web Integration. 5.5.1. The contractor shall interact with service providers, other agencies, and vendors to ensure the efficient and effective operation of web applications. The contractor shall coordinate the interaction of operating systems, portal software infrastructure, COTS products, databases, and applications to ensure efficient application operation and an acceptable user experience. The Web integration support includes: 5.5.2. Advising and coordinating with developers, administrators, network personnel, and architects on changes to the architecture and technical environment. 5.5.3. Participating in the Virtual Architecture Team and assisting in developing and maintaining the USAREC, G6 Enterprise Technical Architecture documents. | Develop and maintain the USAREC G6 Enterprise Technical Architecture; ensure web operation is effective and supports the entire command The contractor shall meet a minimum of 95% of all Applications and Web integration project tasks and milestones Contractor compliance will be monitored for CPAR reporting | RRC, Fort Knox, KY
1.3.7 Database Management and Administration (5.7. Database Management and Administration) | 1.1.2 Enterprise Service Element 1...n (Specify) | Computer and Information Research Scientist, Senior | 5.6. Data Engineering. The contractor shall develop, document, engineer, and integrate logical data models and physical data models in support of a task. Data models shall be constructed daily by Government guidelines and instructions to ensure that developed models are reflected in the Government data engineering processes. Data modeling work products and activities shall include: 5.6.1. Logical Data Models, Physical Data Models, and Entity Relationship Diagrams including those that conform to DOD standards such as the DOD Enterprise Data Model Standards outlined in the DoDAF. 5.6.2. Logical Data Model documentation shall be developed using Computer Assisted Software Engineering tools. | Logical and physical data models will conform with DOD Enterprise Data Model Standards The contractor shall meet 100% of DOD Enterprise Data Model Standards requirements and 95% of all data engineering project tasks and milestones Contractor compliance will be monitored for CPAR reporting | Telework and Alternate Job Locations
1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | 1.1.2.1 Enterprise Service Element Hardware (Specify) | Computer and Information Research Scientist, SME | 5.7. Database Management and Administration. The contractor shall: 5.7.1. Provide support services for Government enterprise databases in development, test, and production environments. This support shall include, but is not limited to: 5.7.1.2. The analysis, transition, and mapping of legacy data and external systems' data, to include identification of data sources, mappings to the automation systems, LDM, and the physical database design, and support for subsequent mapping of the physical data to systems databases. 5.7.1.3. The maintenance of the Production and Data Warehouse Data Dictionaries, ensuring that they follow the DOD Data Standards. 5.7.1.4. Creation of periodic update packages of standardized data elements and submission of those packages to designated Government approval authorities for review and implementation. 5.7.1.5. Conducting periodic database maintenance (daily, weekly, and monthly). Maintenance activities shall be conducted at times approved by the government and that have minimal impact on the organizational mission. 5.7.1.6. Continual monitoring and optimizing of the production database environments in conjunction with host services, including maximizing system performance within the application, maintainability, and reliability. 5.7.1.7. Maintenance of contingency plans to uphold established service levels, execution of backups in support of the plan, and execution of recovery of all database components as required. 5.7.2. Perform a set of regular tasks in support of software applications and related servers that includes the operation and maintenance of Government provided COTS and custom-developed application services and software. Tasks shall include: 5.7.2.1. The installation and management of COTS server-level software to include to MS Project®, SharePoint®, Centra VCS®, SUN ON'E Portal®, Documentum ®, LDAP ®, ePiphany®, Web Trends ®, SumTotal Systems®, e-ROOM ®. 5.7.2.2. The installation and management of Service Oriented Architecture governance, security, and management tools including System and Layer7. 5.7.2.3. Support for the management and technical integration of externally developed applications and modules, and updates thereto, into the enterprise architecture, to include a review of plans, coordination of project milestone events, integration of the item into the appropriate technical layer(s) (including database layer), validation, and deployment. 5.7.2.4. Support custom-coded applications, some of which connect to internal and external data sources on myriad platforms and from a variety of database systems. 5.7.2.5. Implementing security and software upgrade patches. 5.7.2.6. Support for scheduled maintenance periods. 5.7.2.7. Receiving and responding to trouble tickets for enterprise architecture key business and infrastructure applications incidents. | Data management follows DOD Data Standards The contractor shall meet 100% of DOD Data Standards and 95% of all data management project tasks and milestones Contractor compliance will be monitored for CPAR reporting | OCONUS
1.3.9 Project Control (5.9 Project Control) | 1.1.2.2 Enterprise Service Element Software CSCI 1...n (Specify) | Computer and Information Systems Manager, Junior | 5.8. Project Management. The contractor shall provide effective management of project schedule, performance, risks, subcontracts, and related data. The contractor shall follow a Government approved project management process that offers: 5.8.1. Integrated Master Schedule, with clear milestones, which provides accurate and timely schedule and performance information throughout the life cycle of the program. 5.8.2. The conduct of project milestone reviews using a government template. 5.8.3. Risk management to mitigate program and/or project risks and provides for special emphasis on software development efforts through the integration of metrics to monitor program status. 5.8.4. Active participation by contractor's senior management in project administration and problem-solving. 5.8.5. Communications and change management processes that involve all key stakeholders. 5.8.6. Documented procedure for estimating costs and schedules to ensure consistency. 5.8.7. Providing project status reports to the Government on a weekly basis or as deemed needed. | Project Management Reference PWS 5.8 All projects are managed using an Integrated Master Schedule for the life cycle of the project The contractor shall meet 95% of all project tasks and milestones Contractor compliance will be monitored for CPAR reporting | CONUS
1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | 1.1.2.3 Enterprise Service Element Integration, Assembly, Test, and Checkout | Computer and Information Systems Manager, Journeyman | 5.9. Project Control. 5.9.1 The contractor shall provide support to establish and maintain standardized project controls for Government assigned projects and ensure that project schedules are maintained and integrated into one master schedule. The contractor shall conduct Project Control activities including: 5.9.2. Integrate project schedules into an integrated master schedule. 5.9.3. Establish dependencies between related project schedules and report potential impacts to ensure accurate schedules and metrics are provided to Government managers. 5.9.4. Develop and maintain common schedule dictionaries to assist in maintaining integrated schedules. 5.9.5. Build and maintain project Work Breakdown Structures (WBS). 5.9.6. Support scheduling meetings and other meetings as appropriate. 5.9.7. Administer the consolidated time tracking tool, currently MS Project Server. 5.9.8. Provide to the Government earned value, cost and schedule analyses, and ad hoc reports. 5.9.9. Provide training on developing and maintaining project schedules as required and when requested. | Project Control Reference PWS 5.9 Standardized project controls for assigned projects into a single master schedule The contractor shall incorporate all projects into the master schedule within 10 workdays of identification; meet 95% of all project control tasks and milestones Contractor compliance will be monitored for CPAR reporting
1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) | 1.1.3 Enterprise/Management Information System 1...n (Specify) | Computer and Information Systems Manager, Senior | 5.10. Software Integration Engineering. The contractor shall provide Software Integration Engineering support to coordinate the technical architecture and the integration between major components thereof. The function includes: 5.10.1. Overseeing the applications systems architecture and collaborating with development teams, operations staff, and external engineers to ensure systems security compliance, efficiency, integrity, and maximum operational availability within the overall enterprise architecture. 5.10.2. Providing advice and coordination concerning technology insertions into the enterprise architecture. 5.10.3. Creating technical and system views and models by the DODAF. 5.10.4. Assisting in the sustainment of the enterprise architecture technical architecture and its related documentation (in coordination with other technical staff). 5.10.5. Reviewing project scope documents, requirements, procedures, processes design and plans to determine the technical impact on other areas, systems, sub-systems, and modules of the enterprise architecture. 5.10.6. Providing support services to the Government's Virtual Architecture Team, which works to integrate technical projects into the overall architecture by reviewing project technical design plans, to accomplish the following: conduct rapid technical assessments and implementation impacts on selected products and projects; provide support to resolve cross- system/sub-system/module problem identification and resolution; analyze technical infrastructure issues; support the maintenance of technical architecture documentation, diagrams, and views; and support the Government's strategic long- range technical efforts. | Software Integration Engineering Reference PWS 5.10 Coordinate technical architecture and technical architecture within the Enterprise Architecture The contractor shall meet 95% of all Software Integration Engineering tasks and milestones Contractor compliance will be monitored for CPAR reporting
1.3.12 Process Improvement (5.12. Process Improvement) | 1.1.3.1 Business Area Hardware (Specify) | Computer and Information Systems Manager, SME | 5.11. Training Support Services for Recruiting and Retention College. The contractor shall provide: 5.11.1. Technical Support Analyst. Contract Technical Support Analyst(s) are required to up-load tests, lesson plans, and training data into Blackboard and Training Development Capabilities. The Government will ensure the Technical Analyst(s) has access to all required equipment and resources to perform all training development functions to approved standards of the Government. The contractor shall ensure the Technical Analyst(s) execute training activities and functions by the established timeline. The Technical Support Analyst(s) is required via blackboard to make announcements for all users, announcements for instructors (Cadre) only, disseminate new lesson plans, ideas, and courseware, provide Bulletin board capability with threaded discussion topics, provide the conferencing capability for instructor-facilitated classroom discussion, provide chat room capability to process other training support activities as necessary. The requirements for TDC will require CAD, LP, ITP, CMP, SEP, Test, and PE. 5.11.2. Training Analyst. Training Analyst(s) are required to develop, write, and review documents, plans, and or reports for assigned topics or courses within USAREC. The government will ensure that the Training Analyst(s) have access to all required equipment and resources to perform all training development functions to the approved standards of the Government. The Contractor shall ensure the Training Analyst(s) produce the deliverables by the established timeline. The requirements for TDC will be CAD, LP, ITP, CMP, SEP, Test, and PE. 5.11.3. The Technical Support and Training Analyst(s) shall go through an orientation period to learn the RRC organization. The Training Analyst(s) shall become familiar with the target audience of the respective course and review the Program of Instruction (POI). It shall also include familiarization with the respective lesson plan from which the instructors present in the classroom instruction. This period shall be from 30-60 days after recruitment and reception at RRC. 5.11.4. The Technical Support and Training Analyst(s) shall attend meetings, conferences, briefings, and other information- sharing venues when necessary to perform specified tasks under the contract. 5.11.5. The contract Technical Support and Training Analyst(s) shall remain current on Army doctrine, regulations, and other policy and procedural changes. 5.11.6. The Technical Support and Training Analyst(s) shall meet with Subject Matter Experts (SME) and Course Manager to draft lesson plans generated from task analyses on assigned courses in TE 4, and shall play a key role in determining the sequence and order of lesson plans, and the incorporation of applicable technology and design. The contractor shall submit all lesson plans to the COR or designated Government representative for review and approval. 5.11.7. Helpdesk technician to provide troubleshooting, account management, software updating, and imaging computer systems. | Training Support Services for Recruiting and Retention College (RRC) Reference: PWS 5.11 Training Support Services for Recruiting and Retention College (RRC) The contractor shall meet 95% of all project tasks and milestones Contractor compliance will be monitored for CPAR reporting
1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | 1.1.3.2 Business Area Software CSCI 1...n (Specify) | Computer Hardware Engineer, Junior | 5.12. Process Improvement. The contractor shall provide process improvement using industry best-practices. The contractor shall conduct Process Improvement activities including following tasks: 5.12.1. Provide support services to the activities of the organization's Process Action Teams, Software Engineering Process Group, and the Government's software process oversight committee. 5.12.2. Create and maintain the process improvement plan to consolidate in a single document the planning information to systematically improve the organization's process maturity. 5.12.3. Facilitate the creation and/or maintenance of organizational process improvement documentation. 5.12.4. Develop, update, and/or provide appropriate training material to support the training of the processes. 5.12.5. Provide support services in process improvement assessments, including on the organization’s Project Management Methodology and related processes, as required, or when requested. | Reference PWS 5.12: Process Improvement Provide Process Improvement The contractor shall meet 95% of all project tasks and milestones Contractor compliance will be monitored for CPAR reporting
1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | 1.1.3.3 Business Area Integration, Assembly, Test, and Checkout | Computer Hardware Engineer, Journeyman | 5.13. Information Technology Asset Coordinator. The contractor shall provide the asset coordinator: 5.13.1. Responsible for administrative duties within the IT procurement and inventory management function. 5.13.2. Maintains records and databases containing information regarding licenses, warranties, and service agreements for the organization's hardware and software. 5.13.3. Responsible for documenting and tracking IT assets after delivery to ensure all equipment and software are accounted for. | Information Technology Asset Coordinator Reference PWS 5.13 Document, track, issue, and maintain records of information technology assets. The contractor shall meet a minimum of 95% of all Configuration Management project tasks and milestones Contractor compliance will be monitored for CPAR reporting
1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | 1.1.4 External System Interface Development 1...n (Specify) | Computer Hardware Engineer, Senior | 5.14. Telecommunications Control Officer (TCCO). 5.14.1. Process all communications requests within the command to include installation, removal, transfers, and resolving customer inquiries. 5.14.2. Track and monitor various telecommunications services including local and wide area networks, voice mail systems, wireless and digital services, peripheral equipment, offline message preparation equipment, and telephone switch modernization. 5.14.3. Review actions are completed, and a thorough record is maintained to aid in the validation of billed services. 5.14.4. Perform technical reviews. 5.14.5. Compile support documents and reports, identifies, and notify users of problems, and maintain usage reports. 5.14.6. Provide user training and develops procedures and efficient systems operation. 5.14.7. Review and assist to ensure landlines, smartphones, and tablet data transmissions are properly controlled and use the most economical communications means available. 5.14.8. Contact telecommunication carriers, vendors, or communications representatives to obtain estimated costs for requested services including requests for service, coordinating dates of service, and resolving billing problems. 5.14.9. Manage telecommunications program for USAREC. 5.14.10. Provide technical and managerial guidance for communications. 5.14.11. Research, plan and implement new or upgrades to existing telecommunications and/or data communications systems. 5.14.12. Process requests for new telecommunications and or data communications systems. 5.14.13. Obtain clearance to add and delete data in JRMS and GSA Tops Government systems. 5.14.14. Resolve telecommunications incidents, trouble tickets, and requests for information. | Telecommunications Control Officer (TCCO) Reference PWS 5.14 Provide procedures that ensure telephone lines and smartphone, and tablet data transmissions are properly controlled and use the most economical communications means available and users are compliant. Maintain support documents and reports, identify, and notify users of problems, and maintain usage reports. Contractor compliance will be monitored for CPAR reporting
1.3.16 Business Intelligence (5.16. Business Intelligence Experience) | 1.1.4.1 External System Interface Hardware (Specify) | Computer Hardware Engineer, SME | 5.15. Test and Evaluation. The contractor shall provide testing and evaluation: 5.15.1. Types of testing may include: 5.15.1.1. New and existing baseline images and releases 5.15.1.2. New and existing operational releases 5.15.1.3. New and existing GOTS and COTS applications 5.15.1.4. Access methods and associated security 5.15.1.5. Application security testing 5.15.1.6. Technology projects 5.15.1.7. Hardware configurations (i.e., printers, scanners, and other supportive devices) 5.15.2. The contractor shall perform a set of regular tasks in support of the application administrations that includes the operation and maintenance of the government-provided test and evaluation toolsets and related hardware. Tasks shall include: 5.15.2.1. Customize/code application modules and data fields to support metric collections and processes improvement. 5.15.2.2. Implement security and software upgrade patches. 5.15.2.3. Provide validation of test toolsets as required. 5.15.2.4. Receive and respond to trouble tickets for the testing toolset within 24 hours. 5.15.2.5. Coordinate formal requirements, delivery, and administration of the enterprise test and evaluation toolset. 5.15.2.6. Design, maintain and administer the centralized and secure repository. 5.15.2.7. Collaborate with system administrators and vendors to ensure operations of the testing toolset. 5.15.2.8. Participate in the configuration and testing of test toolset changes | Test and Evaluation Reference PWS 5.15 Ensure coordination between the development and deployment of hardware and software products The contractor shall ensure 100% of all hardware and software products are coordinated before release; meet a minimum of 95% of all project tasks and milestones are Contractor compliance will be monitored for CPAR reporting
1.3.17 General System Support (5.17 General System Support) | 1.1.4.2 External System Interface Software CSCI 1...n (Specify) | Computer Network Architect, Junior | 5.16. Business Intelligence Experience. The contractor shall: 5.16.1. Applies industry-standard strategies and technologies used for the data analysis of business information. 5.16.2. Plan and execute software installations, upgrades, and configurations for Business Intelligence tools. 5.16.3. Visualize data using a variety of methods such as reports and dashboards to support smart business decisions. 5.16.4. Perform data analysis and data modeling to identify historical, current, and predictive trends and insights of business operations. 5.16.5. Business Intelligence specific proficiency in MS Office applications such as Access and Excel; query languages such as to SQL; commercial BI applications such as Power BI; and cloud environments such as Army 365 and Azure. 5.16.6. Administration and maintenance of Army data analytics system of record. 5.16.7. Inspect & Assess data sources and databases. 5.16.8. Collaborate with the government to address BI Project needs. Translate business requirements into a business dimensional model, key subject areas, dimensions, hierarchies, attributes, and measures. | Business Intelligence Experience Reference PWS 5.16 Conduct Oracle-based OBIEE applications and configurations integrating Metadata Repository data The contractor shall ensure 100% of all hardware and software products are coordinated before release; meet a minimum of 95% of all project tasks and milestones Contractor compliance will be monitored for CPAR reporting
1.3.18 Helpdesk Support (5.20. Incident Management (Split amongst locations)) | 1.1.4.3 External System Interface Integration, Assembly, Test, and Checkout | Computer Network Architect, Journeyman | 5.17 General System Support. The contractor shall: 5.17.1. Perform WebLogic administration and multi-server management. 5.17.2. Provide technical training materials and seek mentoring opportunities to promote growth and increase competency. 5.17.3. Work requires experience with DAC, Informatica 7. x, 8. x. 5.17.4. Promote team creativity and cohesiveness to ensure that technical designs fit into the overall data warehouse architecture and to facilitate fairness while striving for consensus in problem-solving. 5.17.5. Metadata and Content Management. 5.17.5.1. Collaborate with DBAs, Data Integration, Metadata, and BI Delivery Team to address BI Project needs 5.17.5.2. Devise & analyze BI Metadata/Logical Data Model in a graphics chart 5.17.5.3. Translate BI requirements into analytics metadata Devise & Test Metadata 5.17.5.4. Collaborate with IT BI SMEs to define high-level report/analysis, iBots/alerts, and overall intelligence dashboard functionality and user experience 5.17.5.5. Design & Build BI Delivery components (Dashboards, Reports, BI Publisher bigots, etc.) 5.17.5.6. Perform performance tuning as it regards OBIEE reports (i.e., where are calculations performed, etc.) 5.17.6. Defining Requirements and Customer Technical Support. 5.17.6.1. Coordinate interactions with customers and business analysts to establish common business information requirements, analyze data to satisfy those requirements, and execute specific technical solutions to achieve stated business goals 5.17.6.2. Strive to exceed customer expectations in the delivery of BI solutions for dashboards, BI Publisher reports, and Ad- hoc requests 5.17.6.3. Proactively prevent and support resolution of data quality issues, improve query performance, and pro-vide report development coaching and guidance throughout the BI power user community 5.17.6.4. Communicate an understanding of the importance of compliance with corporate, regulatory, and internal security policies when administering and configuring the OBIEE/OBIA reporting platform 5.17.6.5. Help end-users and business analysts fully understand the technical options when solving business requirements and developing BI reporting solutions that enhance and extend the end-user usability experience 5.17.6.6. Prepare and present project reports for IT and Business management 5.17.6.7. Implement Policy and Standards 5.17.6.8. Perform Project Status 5.17.6.9. Perform Test plan preparation 5.17.6.10. Install and configure computer systems 5.17.6.11. Diagnose and solve hardware/software issues 5.17.6.12. Provide management/user in resolving complex automated support problems Interfaces include but are not limited to: HTML; Hyperion; Visual Basic; JAVA; JavaScript VB Script; ASP; Perl; and CGI scripts, and applications will run under UNIX (Solaris), and Windows NT 4.0. HTTP connectivity will be hosted using Netscape and Microsoft IIS Web Servers. Applications will interface with Oracle 8 databases using Open Database Connectivity (ODC) and other application programming interfaces (API). | General System Support Reference PWS 5.17 Provide management/user in resolving complex automated support problems The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
1.3.19 IT Administrative Support Services (5.22. Support the administration of the IT workforce readiness & 5.23. Administrative Support) | 1.1.5 System Level Infrastructure (Specify) | Computer Network Architect, Senior | 5.18. Computer Graphics (CG) Provide graphics using applications such as Adobe Photoshop and Adobe Illustrator. | Computer Graphics (CG) Reference PWS 5.18 Applications used include, but are not limited to, Adobe Photoshop; Adobe Illustrator; Adobe Premiere The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting
5.18. Computer Graphics (CG) | 1.1.5.1 System Level Hardware (Specify) | Computer Network Architect, SME | 5.19. Technical Writers: The contractor shall provide qualified personnel to maintain and manage the yearly updating regulations, manuals, memorandums, and forms. The contractor shall submit all work products to the COR or designated Government representative for review and approval. 5.19.1 The contractor shall provide qualified personnel to type, review, edit, and publish e-documents, regulations, forms, and pamphlets utilizing Microsoft Excel, Share Point, PowerPoint, MSWord, Adobe Pro, Adobe Creative Suite, Lotus Forms, PDF Filler, and publication websites. Personnel will also review and edit business cards submitted by recruiting force. The contractor shall submit all work products to the COR or designated Government representative for review and approval. 5.19.2 The contractor shall establish filings and records IAW established DOD and USAREC guidelines. 5.19.3 The contractor shall receive and enter information into the web file database using Excel and Share Point. | Technical Writers Reference PWS 5.19 The contractor shall provide qualified personnel to maintain and manage the yearly updating regulations, manuals, memorandums, and forms. The contractor shall submit all work products to the COR or designated Government representative for review and approval The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
5.19. Technical Writers | 1.1.5.2 Service Infrastructure 1...n (Specify) | Computer Network Support Specialist, Junior | 5.20. Incident Management 5.20.1 Contractor shall provide technical resolution for an average of 4,000-6,000 incident tickets per month Incidents are submitted by approximately 13,000 users located within the USAREC Headquarters building (Fort Knox), Army Marksmanship Unit (AMU) (Fort Benning), Special Operations Recruiting Battalion (SORB) (Fort Bragg), Recruiting and Retention Collage (RRC) (Fort Knox), and across USARECs 1800+ Brigades, Battalions, Companies and Stations worldwide. 80% of incidents should be resolved during the first contact and 100% within 72 hours. Contractor must be capable of serving as subject matter experts (SME) on common and advanced incident topics as described below and liaison with external agencies, vendors, and key stakeholders to resolve incidents, problems, and events. 5.20.1.1. Common USAREC desktop support incident tickets may include: IN/OUT Processing, Asset Management, Provisioning User IT Equipment, Networking and Connectivity, Software Licenses Management, Entitlement Management, Account Management, Printer Configuration and Networking, Hardware/Software Troubleshooting, Email/Mailbox/Distribution List Requests, Secure Host Baseline (SHB)/ Operating System Issues, A365 and other Cloud Platform Issues, Government/Commercial Systems and Applications, IT Hardware Repair, and Providing Basic IT Support and User Training. 5.20.1.2. Common USAREC biometric (fingerprinting) support incident tickets may include Hardware/Software troubleshooting, Account/License/Entitlement Management, Hardware Provisioning, Asset Management, Assisting the Field in Obtaining Missing Reports, Facilitating Approval for Waiver/Exception Requests, Individual and Group Training on the Use of Biometric Technology. 5.20.1.3. Common USAREC mobility support incident tickets may include Mobile Device Provisioning/Configuration, Mobile Device Management (MDM), Security Compliance, Account Management, Number Porting, Asset Management, Coverage Issues, New Technology Implementations, Mobile Security, Mobile Applications. 5.20.1.4. Common USAREC cyber support incident tickets may include New User Accounts in various GOTS and COTS applications/systems, ATCTS, ACAS, Social Media Threats, VIP reports, CAC Registration, General Cyber Inquiries, User Violation Notices, Investigations, Requests for Information, Certifications, and training. 5.20.1.5. Common USAREC information management incident tickets may include Requests for Business Cards, Freedom of Information Act (FOIA) and Privacy Act inquiries, and Army Records Management requests. 5.20.2. Contractor shall provide troubleshooting, account management, software updating, and imaging for over 140 computer systems for Army Marksmanship Unit (AMU) located at Ft Benning, Ga. The technician will be responsible for keeping computer systems performing in a global environment. The technician will also be responsible for troubleshooting complex target systems to ensure the team can practice before all competitive shooting matches. 5.20.3. Contractor shall provide troubleshooting, account management, software updating, and imaging for over 45 computer systems for Special Operations Recruiting Battalion located at Fort Bragg NC. 20 computers are globally dispersed throughout CONUS AND OCONUS locations. Travel may be required for emergencies. Computing systems are vital to the SORB mission of providing Soldiers with the essential missions as determined by Congress, the Department of Defense, and the Army leadership. 5.20.4. Contractor shall provide helpdesk technicians for troubleshooting biometrics systems (physical and digital identification) within the command. The Department of the Army mandates the physical and digital identification of all potential enlistees. Biometric systems are prone to have technical issues thus a technician is warranted. Physical and digital identity is vital to the Army to eliminate known criminals from entering the Army enlistment process before expending millions of dollars on unqualified applicants. The Army is missioned to enlist upwards of 80,000 applicants every year. To get the number of applicants needed, recruiters will process upwards of 200,000. All applicants must have biometrics on file to determine moral qualifications before or after enlistment. This position is vital to ensure software and equipment issues are resolved expeditiously to keep the flow of applicants flowing through the arduous process. Technician receives, on average, 20-30 tickets per day. 5.20.5. Create and maintain knowledge articles related to incidents. 5.20.6 Problem and Event Management. Contractor shall identify risks, secondary impacts, and systemic problems that are reported from end users, service providers, other agencies, and commercial vendors. Problems should be promptly reported, assigned/escalated to the appropriate resource for resolution, and tracked through resolution. | Incident Management Reference PWS 5.20 Contractor shall: provide helpdesk technicians in support of incident management tasks; maintain knowledge articles related to incidents; contractor shall maintain expertise in incident types. The contractor shall resolve 80% of incidents upon first contact and 100% within 3 business days of initial contact. Contractor compliance will be monitored for CPAR reporting.
5.21. Information Management Services | 1.2 System Level Integration | Computer Network Support Specialist, Journeyman | 5.21. Information Management Services 5.21.1. Provide office management, communication, and word processing support. 5.21.2. Provide support for the FOIA, Privacy Act, IT Records Management, IT Content Management, and IT HR Compliance Programs. 5.21.3. Receive and process inbound requests. 5.21.4. Verify documents that follow established regulations. 5.21.5. Work within designated systems of record to manage cases, documents, records, and other content. 5.21.6. Perform record searches. 5.21.7. Review and mark records as appropriate. 5.21.8. Generate responses to requests for Government approval and dissemination. 5.21.9. Maintain official office records, such as mail distribution lists and electronic signatures. 5.21.10. Maintain statistical and narrative data related to administrative services programs and generate reports. 5.21.11. Maintain awareness of policies, statutory law, regulations, organizational, and government-wide issues that impact the various Administrative Services Programs. | IT Information Management Reference PWS 5.21 Maintain awareness of policies, statutory law, regulations, organizational, and government-wide issues that impact the various Administrative Services Programs The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
5.24 Network Operations | 1.3 Systems Engineering | Computer Network Support Specialist, Senior | 5.22. Support the administration of the IT workforce readiness. 5.22.1. Maintain up-to-date records, including organizational charts, of IT workforce readiness, including authorizations, filled and vacant positions, in and inbound and outbound personnel. 5.22.2. Maintain up-to-date records of IT certifications across the workforce. 5.22.3. Monitor sources such as the Digital Technology Career Field website and Army Career Program 34 website to identify training opportunities for the IT workforce. 5.22.4. Support maintenance of position and job descriptions. 5.22.5. Serve as SME and supports the management and review of policy and procedural compliance of USAREC IT information systems. 5.22.6. Administrate digital content on Army and commercial standard platforms. 5.22.6.1. Using Army and commercial industry-standard platforms, such as Army 365, to support business processes and create assets, including team sites, pages, lists, libraries, calendars, and workflows. 5.22.6.2. Provide account management support. 5.22.6.3. Maintain Command-wide channels to collect, disseminate, and communicate training, policy, procedural, and organizational updates. 5.22.6.4. Provide configuration, customization, and administration of Army and commercial standard platforms. This may include customizing screens, editing fields, creating workflows, configuring reports, user account management, permissions, and roles, configuring security and privacy settings. 5.22.6.5. Provide support services for the test, evaluation, and implementation of new and emerging web-based server services and technologies. | Support the administration of the IT workforce readiness Reference PWS 5.22 Provide configuration, customization, and administration of Army and commercial standard platforms. The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
5.25. Cyber Security | 1.3.1 Software Systems Engineering | Computer Network Support Specialist, SME | 5.23. Administrative Support. The Contractor shall coordinate calendars to include setting and confirming appointments. Meeting preparation to include collecting and distributing read-a heads, appointment reminders, and connecting comms. Preparing documentation to include letters, memoranda, and briefings. Responsible for the completion and submission of the Daily Status Report (Perstat). Call screening. Task administration to include TMT Taskers, CIO tasks, Taskers, etc. Tracking mandatory training compliance for personnel, including updating DTMS and other systems of record. Attend administrative meetings, take minutes, and distribute minutes as necessary within three business days. Coordinate travel in DTS. | Administrative Support Reference PWS 5.23 The Contractor shall coordinate calendars to include setting and confirming appointments. Meeting preparation to include collecting and distributing read-a heads, appointment reminders, and connecting comms. The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
| 1.3.2 Integrated Logistics Support (ILS) Systems Engineering | Computer Operator, Junior | 5.24 Network Operations. 5.24.1 Monitor network, system and application performance and work with government identified service providers to resolve issues such as outages, service degradation, upgrades, and maintenance. Networks include commercial and government hardwired and mobile networks providing internet, data, voice, fax, and other telecommunications services. Systems and applications include both GOTS and COTS products. 5.24.2 Plan system and network maintenance events with service provider and USAREC functional leads to ensure minimal disruptions to Recruiting operations. 5.24.3 Create, manage, ensure compliance and report against Army, TRADOC, and USAREC operations orders, taskings, etc. 5.24.4 Lead, plan, represent USAREC interests in coordination meetings with service providers, industry partners and other stakeholders. 5.24.5 Maintain communications channels with subordinate units and other staff sections. | Network Operations Reference PWS 5.24 Contractor shall manage IT operations, monitor network/system/application performance and coordinate on behalf of G6 with service providers, external agencies, and service providers. The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
| 1.3.3 Cybersecurity Systems Engineering | Computer Operator, Journeyman | 5.25. Cyber Security. Protect USAREC users, devices, systems, and data from unauthorized access or criminal use. through timely resolution of user requests, investigation of potential threats, user training programs, support for audits and inspections, and enterprise-wide communications/notifications/reporting. Serve as subject matter experts (SME) on common and advanced cyber topics as described below and liaison with external agencies, vendors, and key stakeholders to resolve cyber incidents, problems, and events. 5.25.1. Common USAREC Cyber support incidents may include Provisioning user accounts, ACTCS, REQUEST accounts, ACAS, Remedy, Social Media Threats, VIP reports, CAC registration, General Cyber Inquiries, User Violation Notifications, VIP Database Inputs. | Cyber Security Reference PWS 2.25 Contractor shall protect USAREC users, devices, systems, and data from unauthorized access or criminal use through timely resolution of user requests, investigation of potential threats, user training programs, support for audits and inspections, and communications/notifications/reporting The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
| 1.3.4 Core Systems Engineering | Computer Operator, Senior | 5.26. Monthly Report. Summary of accomplishments during the reporting period and significant events. Deliverables submitted or progress on deliverable products. Any current or anticipated problems. Summary of activity planned for the next reporting period. | Contract Deliverables Reference PWS 5.26 Satisfactory service(s) is/are considered the acceptable deliverable(s). Specific requirements shall be forwarded, to the COR (in writing), as work orders and presented to the contractor for evaluation. The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
| 1.3.5 Other Systems Engineering 1...n (Specify) | Computer Operator, SME | 5.27. Minimum Qualifications: The contractor shall: 5.27.1. By DOD Regulation 8570.01-M paragraphs C1.4.4.12, C7.3.4.4, C1.4.4.5, C2.1.5, C1.4.4.12, C3.2.4.8.1 and C4.2.3.1, contractor employees with privileged access to any information system, contractors performing described Information Assurance (IA) functions must satisfy both preparatory and sustaining DOD IA training and certification requirements. Any personnel hired to perform functions in a position deemed as requiring elevated access privileges must be able to attain the security background check needed for the functions required. There are other determining factors regarding whether a user is placed in one of these training groups. More information on Approved Baseline Certifications can be found here: https://public.cyber.mil/cw/cwmp/dod-approved- 8570-baseline-certifications/ | Minimum Qualifications Reference PWS 5.27 By DOD Regulation 8570.01-M paragraphs C1.4.4.12, C7.3.4.4, C1.4.4.5, C2.1.5, C1.4.4.12, C3.2.4.8.1 and C4.2.3.1, contractor employees with privileged access to any information system, con-tractors performing described Information Assurance (IA) functions must satisfy both preparatory and sustaining DOD IA training and certification requirements The contractor shall meet a minimum of 95% of all integration objectives, timelines, and milestones Contractor compliance will be monitored for CPAR reporting.
| 1.4 Program Management | Computer Programmer, Junior
| 1.4.1 Software Program Management | Computer Programmer, Journeyman
| 1.4.2 Integrated Logistics Support (ILS) Program Management | Computer Programmer, Senior
| 1.4.3 Cybersecurity Program Management | Computer Programmer, SME
| 1.4.4 Core Program Management | Computer Systems Analyst, Junior
| 1.4.5 Other Program Management 1...n (Specify) | Computer Systems Analyst, Journeyman
| 1.5 Change Management | Computer Systems Analyst, Senior
| 1.6 Data Management | Computer Systems Analyst, SME
| 1.7 System Test and Evaluation | Computer Systems Engineer_Architect, Junior
| 1.7.1 Developmental Test and Evaluation | Computer Systems Engineer_Architect, Journeyman
| 1.7.1.1 Cybersecurity Test and Evaluation | Computer Systems Engineer_Architect, Senior
| 1.7.1.2 Other DT&E Tests 1…n (Specify) | Computer Systems Engineer_Architect, SME
| 1.7.2 Operational Test and Evaluation | Computer User Support Specialist, Junior
| 1.7.2.1 Cybersecurity Test and Evaluation | Computer User Support Specialist, Journeyman
| 1.7.2.2 Other OT&E Tests 1…n (Specify) | Computer User Support Specialist, Senior
| 1.7.3 Mock-ups/System Integration Labs (SILs | Computer User Support Specialist, SME
| 1.7.4 Test and Evaluation Management/Support | Data Warehousing Specialist, Junior
| 1.7.5 Test Facilities | Data Warehousing Specialist, Journeyman
| 1.8 Training | Data Warehousing Specialist, Senior
| 1.8.1 Equipment | Data Warehousing Specialist, SME
| 1.8.2 Services | Database Administrator, Junior
| 1.8.3 Facilities | Database Administrator, Journeyman
| 1.8.4 Training Software 1...n (Specify) | Database Administrator, Senior
| 1.9 Data | Database Administrator, SME
| 1.9.1 Data Deliverables 1...n (Specify) | Database Architect, Junior
| 1.9.2 Data Repository | Database Architect, Journeyman
| 1.9.3 Data Rights 1...n (Specify) | Database Architect, Senior
| 1.10 Peculiar Support Equipment | Database Architect, SME
| 1.10.1 Test and Measurement Equipment | Document Management Specialist, Junior
| 1.10.2 Support and Handling Equipment | Document Management Specialist, Journeyman
| 1.11 Common Support Equipment | Document Management Specialist, Senior
| 1.11.1 Test and Measurement Equipment | Document Management Specialist, SME
| 1.11.2 Support and Handling Equipment | Geographic Information Systems Technician, Junior
| 1.12 Operational Infrastructure/Site Activation by Site 1...n (Specify) | Geographic Information Systems Technician, Journeyman
| 1.12.1 Initial Hardware Procurement | Geographic Information Systems Technician, Senior
| 1.12.1.1 End User Equipment | Geographic Information Systems Technician, SME
| 1.12.1.2 Cybersecurity Equipment | Geospatial Information Scientist and Technologist, Junior
| 1.12.1.3 IT Infrastructure and Enterprise Software Equipment | Geospatial Information Scientist and Technologist, Journeyman
| 1.12.1.4 Other 1...n (Specify) | Geospatial Information Scientist and Technologist, Senior
| 1.12.2 Initial Software License Procurement | Geospatial Information Scientist and Technologist, SME
| 1.12.2.1 End User Software License | Information Security Analyst, Junior
| 1.12.2.2 Cybersecurity Software Licenses/Services | Information Security Analyst, Journeyman
| 1.12.2.3 IT Infrastructure and Equipment | Information Security Analyst, Senior
| 1.12.2.4 Other 1...n (Specify) | Information Security Analyst, SME
| 1.12.3 Initial Software Release (Pre-IOC) Modification/Enhancement | Information Technology Project Manager, Junior
| 1.12.3.1 Routine Fixes/Deficiency Correction | Information Technology Project Manager, Journeyman
| 1.12.3.2 Deployment Independent Verification and Validation | Information Technology Project Manager, Senior
| 1.12.3.3 Installation/Test | Information Technology Project Manager, SME
| 1.12.4 Site Activation | Management Analyst, Junior
| 1.12.4.1 Data Migration | Management Analyst, Journeyman
| 1.12.4.2 User Training | Management Analyst, Senior
| 1.12.4.3 User Documentation | Management Analyst, SME
| 1.12.4.4 Management/Engineering Support | Network and Computer Systems Administrator, Junior
| 1.12.4.5 Site Installation, Test, and Checkout | Network and Computer Systems Administrator, Journeyman
| 1.12.5 Interim Operations and Support (Pre-IOC) | Network and Computer Systems Administrator, Senior
| 1.12.5.1 Help Desk | Network and Computer Systems Administrator, SME
| 1.12.5.2 System Database Administrator | Software Developer_Applications, Junior
| 1.12.5.3 Installation, Test, and Checkout | Software Developer_Applications, Journeyman
| 1.12.5.4 IT Equipment Maintenance | Software Developer_Applications, Senior
| 1.13 Industrial Facilities | Software Developer_Applications, SME
| 1.13.1 Construction/Conversion/Expansion | Software Developer_Systems Software, Junior
| 1.13.2 Equipment Acquisition or Modernization | Software Developer_Systems Software, Journeyman
| 1.13.3 Maintenance (Industrial Facilities) | Software Developer_Systems Software, Senior
| 1.14 Initial Spares and Repair Parts | Software Developer_Systems Software, SME
Software Quality Assurance Engineer and Tester, Junior
Software Quality Assurance Engineer and Tester, Journeyman
Software Quality Assurance Engineer and Tester, Senior
Software Quality Assurance Engineer and Tester, SME
Technical Writer, Junior
Technical Writer, Journeyman
Technical Writer, Senior
Technical Writer, SME
Telecommunications Engineering Specialist, Junior
Telecommunications Engineering Specialist, Journeyman
Telecommunications Engineering Specialist, Senior
Telecommunications Engineering Specialist, SME
Telecommunications Equipment Installer and Repairer, Junior
Telecommunications Equipment Installer and Repairer, Journeyman
Telecommunications Equipment Installer and Repairer, Senior
Telecommunications Equipment Installer and Repairer, SME
Training and Development Specialist, Junior
Training and Development Specialist, Journeyman
Training and Development Specialist, Senior
Training and Development Specialist, SME
Video Game Designer, Junior
Video Game Designer, Journeyman
Video Game Designer, Senior
Video Game Designer, SME
Web Administrator, Junior
Web Administrator, Journeyman
Web Administrator, Senior
Web Administrator, SME
Web Developer, Junior
Web Developer, Journeyman
Web Developer, Senior
Web Developer, SME

## ROM BOE
Proprietary; Procurement Sensitive The information in this document is proprietary. It may not be used, reproduced, disclosed, or exported without written approval.
Table 1
| CLIN | FTEs | hours | totals | 1.3.1 Functional Support (5.1. Functional Support) | 1.3.2 Requirements Engineering (5.2. Requirements Engineering) | 1.3.3 Business Process Modeling (5.3. Business Process Modeling) | 1.3.4 Software Engineering (5.4. Software Engineering) | 1.3.5 Applications and Web Integration (5.5. Applications and Web Integration) | 1.3.6 Data Engineering (5.6. Data Engineering) | 1.3.7 Database Management and Administration (5.7. Database Management and Administration) | 1.3.8 Project Management (5.8. Project Management & 5.26. Monthly Report & 5.27. Minimum Qualifications ) | 1.3.9 Project Control (5.9 Project Control) | 1.3.10 Software Integration Engineering (5.10. Software Integration Engineering.) | 1.3.11 Training Support Services for Recruiting and Retention College (RRC) (5.11. Training Support Services for Recruiting and Retention College) | 1.3.12 Process Improvement (5.12. Process Improvement) | 1.3.13 Information Technology Asset Coordinator (5.13. Information Technology Asset Coordinator) | 1.3.14 Telecommunications Control Officer (TCCO) (5.14. Telecommunications Control Officer (TCCO)) | 1.3.15 Test and Evaluation (5.15. Test and Evaluation & 1.6.1 QA/QC and 1.6.2 QASP) | 1.3.16 Business Intelligence (5.16. Business Intelligence Experience) | 1.3.17 General System Support (5.17 General System Support) | 1.3.18 Helpdesk Support (5.20. Incident Management (Split amongst locations)) | 1.3.19 IT Administrative Support Services (5.22. Support the administration of the IT workforce readiness & 5.23. Administrative Support) | 5.18. Computer Graphics (CG) | 5.19. Technical Writers | 5.21. Information Management Services | 5.24 Network Operations | 5.25. Cyber Security | 8(a) STARS
Program Manager/Corporate Liaison | 0002 | 1 | 1872 | 1872 | [7 empty] | 1872 | [16 empty] | Information Technology Project Manager
Transition Manager | 0001 | 0.125 | 234 | 234 | [7 empty] | 234 | [16 empty] | Information Technology Project Manager
Project Manager | 0002 | 3 | 5616 | 5616 |  |  |  | 374.4 | 374.4 | 374.4 | 374.4 | 1123.2 | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | [8 empty] | Information Technology Project Manager
Solutions Architect | 0002 | 1 | 1872 | 1872 |  |  |  | 655.2 | 280.8 | 280.8 | 468 |  |  | 187.2 | [14 empty] | Computer Systems Engineer/Architect
Systems Engineer | 0002 | 2 | 3744 | 3744 |  |  |  | 1872 | 936 |  |  |  |  | 936 | [14 empty] | Computer Systems Engineer/Architect
Software Developer | 0002 | 3 | 5616 | 5616 | 936 |  |  | 936 | 468 |  | 1872 |  |  | 468 |  |  |  |  | 936 | [9 empty] | Software Developer, Applications
Network Engineer | 0002 | 1 | 1872 | 1872 |  |  |  | 468 | 234 | [8 empty] | 234 | [8 empty] | 936 |  | Computer Network Support Specialist
Network Administrator | 0002 | 1 | 1872 | 1872 | [22 empty] | 1872 |  | Computer Network Support Specialist
Web Development Specialist | 0002 | 1 | 1872 | 1872 |  |  |  |  | 1872 | [19 empty] | Web Developer
UI/UX Designer / Computer Graphics Specialist | 0002 | 1 | 1872 | 1872 |  |  |  | 1310.4 | [5 empty] | 187.2 | [9 empty] | 374.4 |  |  |  |  | Web Developer
Technical Editor/Writer | 0002 | 2 | 3744 | 3744 |  |  |  | 1872 | 187.2 |  |  |  |  | 187.2 | [8 empty] | 187.2 |  | 1123.2 | 187.2 |  |  | Technical Writer
QA/Testing Specialists | 0002 | 2 | 3744 | 3744 |  |  |  | 748.8 |  |  | 936 |  |  | 187.2 |  |  |  |  | 1872 | [9 empty] | Software Quality Assurance Engineer and Tester
Quality Assurance Manager | 0002 | 1 | 1872 | 1872 | [7 empty] | 187.2 |  |  |  | 1497.6 |  |  | 187.2 | [9 empty] | Senior Software Quality Assurance Engineer and Tester
Data Architect | 0002 | 1 | 1872 | 1872 | 187.2 |  | 187.2 | 187.2 | 187.2 | 374.4 | 374.4 |  |  | 187.2 | [6 empty] | 187.2 | [7 empty] | Database Architect
Telecom Control Officer | 0002 | 1 | 1872 | 1872 | [13 empty] | 1872 | [10 empty] | Telecom Engineering Specialist
Database Administrator | 0002 | 1 | 1872 | 1872 | [5 empty] | 468 | 1404 | [17 empty] | Database Administrator
Cyber Security Specialist | 0002 | 2 | 3744 | 3744 | [23 empty] | 3744 | Information Security Analyst
Business Analyst | 0002 | 6 | 11232 | 11232 | [5 empty] | 936 | 936 |  |  |  | 3744 | 936 | 936 | 936 | 936 | 1872 | [8 empty] | Business Intelligence Analyst
Scheduler | 0002 | 1 | 1872 | 1872 | [8 empty] | 1872
Training Specialist | 0002 | 1 | 1872 | 1872 |  |  |  | 187.2 | [5 empty] | 187.2 | 1497.6 | [13 empty] | Training and Development Specialist
SME - Process Improvement, Business Intelligence | 0002 | 2 | 3744 | 3744 | [11 empty] | 1872 |  |  |  | 1872 | [8 empty] | Business Intelligence
Service Desk Technician | 0003 | 8.5 | 15912 | 15912 | [12 empty] | 1872 | 1872 | 1872 |  |  | 10296 | [6 empty] | Computer User Support Specialist
Service Desk Manager | 0002 | 1 | 1872 | 1872 | [12 empty] | 93.6 | 93.6 |  |  |  | 1684.8 | [6 empty] | Computer Network Support Specialist
Asset / O&M Manager (Configuration Mgmt) | 0002 | 1 | 1872 | 1872 |  |  |  | 187.2 | [5 empty] | 187.2 |  |  | 1310.4 |  | 187.2 | [9 empty] | Management Analyst
Clerk / Administrative Assistant | 0003 | 1 | 1872 | 1872 | [22 empty] | 1872
|  | 45.625 | 85410 | 85410 | 1123.2 | 0 | 187.2 | 8798.4 | 4539.6 | 2433.6 | 6364.8 | 3416.4 | 2246.4 | 3088.8 | 5616 |  | 4586.4 | 5382 | 6364.8 | 4118.4 | 187.2 | 11980.8 | 187.2 | 374.4 | 1123.2 | 187.2 | 4680 | 3744
[5 empty] | 0.6 | 0 | 0.1 | 4.7 | 2.425 | 1.3 | 3.4 | 1.825 | 1.2 | 1.65 | 3 |  | 2.45 | 2.875 | 3.4 | 2.2 | 0.1 | 6.4 | 0.1 | 0.2 | 0.6 | 0.1 | 2.5 | 2
related to 1.3.4
Proprietary; Procurement Sensitive The information in this document is proprietary. It may not be used, reproduced, disclosed, or exported without written approval.